## Project Schedule (v1) (hidden)
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  | OCBC Data Lineage RFP - POC | [9 empty] | 2022-02-14
Enter Company Name in cell B2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  |  |  |  | Project Start: | [6 empty] | 2022-02-14
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  |  |  |  | Display Week: | [6 empty] | 1 |  |  |  | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-02-14 to 2022-04-17
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | S/N | TASK | DEPENDENCIES | END/EXPECTED COMPLETION DATE | ASSIGNED TO | Tested in IBM Environment? | EFFORT | CUMULATIVE MAN-DAY EFFORT | STATUS | COMMENTS | PROGRESS | START | END |  | DAYS | time axis 2022-02-14 to 2022-04-17
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule. | bar: 2022-03-25; 2022-04-06
| A | Testing in IBM Environment |  |  | Hung / John / Son |  |  |  | Completed |  | 100% | 2022-01-18 | 2022-01-18
| B | Dropbox access (file 8.6 gb) |  |  | OCBC / Clement / Anindyo |  | 2 |  | On-Track | Small files in Dropbox, but oCBC has not been notified > have not enabled the hard disk // Anindyo will go on site today | 100% | 2022-02-14 | 2022-02-15
| C | Harddisk access |  |  | OCBC / Anindyo / John |  | 5 | 1 | Pending | OCBC has provided 2 machine > IBM has 2 hard disk ready for file transfer (done concurrently) and best-case: complete the file transfer by EOD | 50% | 2022-02-14 | 2022-02-18 | 2022-02-14 | 2022-02-14
| 1 | Env readiness (VMs) |  |  | OCBC (Parteek/Clement) |  |  |  | Completed | Update: OCBC will provide the VM and IBM will do the OCP installation | 100% | 2022-02-14 | 2022-02-14
| 1.1 | OCP Pre-requsitie (Domain name and Network) |  |  | Hung / John |  | 1 | 1 | Completed |  | 100% | 2022-02-14 | 2022-02-14
| 1.2 | OCP installation (Redhat) |  |  | Hung / John |  | 1 | 1 | Completed |  | 100% | 2022-02-14 | 2022-02-14
| 1.3 | Share the hard disk to Anindyo |  |  | Daryl |  |  |  | Completed |  | 100% | 2022-01-13 | 2022-01-13
| 1.4 | Provide the link url and get the RH assistance resource to our upcoming meeting cadence |  |  | John |  |  |  | Completed |  | 100% | 2022-01-13 | 2022-01-13
| 2 | Trial License |  |  | Clement |  | 3 | 3 | Completed | Clement has send a follow up to respond on whether the specific clause (provided by OCBC) is sufficient. // OCBC has replied on the approval of the license agreement | 100% | 2022-02-14 | 2022-02-16
| 3 | Download binaries to local repo |  |  | Son / Hung |  | 3 |  | Completed |  | 100% | 2022-01-14 | 2022-01-18
| 4 | OpenShift install | 1,2,3,C | 2022-02-18 | John / Hung |  | 5 |  | Not Started | Hung might not be able to get down onsite, Anindyo / OCBC might be setting up | 0% | 2022-02-21 | 2022-02-25
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | 5 | CP4D Install | 4 | 2022-02-18 | John |  | 7 | 15 | Not Started | Hung Downloaded CP4D v 4.0.5 but has some issue, John will conduct the download and check the progress | 0% | 2022-02-28 | 2022-03-08 |  | 9
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 5.1 | a) Verify environment | 4 |  | John |  |  |  | Not Started |  | 0% | 2022-02-28 | 2022-03-08 |  | 9
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | 5.2 | b) Copy binaries to Private Registry | 4 |  | John |  |  |  | Not Started |  | 0% | 2022-02-28 | 2022-03-08 |  | 9
| 5.3 | c) Foundation steps | 4 |  | John |  |  |  | Not Started |  | 0% | 2022-02-28 | 2022-03-08 |  | 9
| 5.4 | d) Install required services | 4 |  | John |  |  |  | Not Started |  | 0% | 2022-02-28 | 2022-03-08 |  | 9
| 6 | Manta Install | 1,2 | 2022-02-18 | Anindyo |  | 2 | 5 | Not Started | Klook Integration | 0% | 2022-02-17 | 2022-02-18
| 7 | Manta integration | 6 | 2022-02-18 | Anindyo |  | 2 | 7 | Not Started |  | 0% | 2022-02-21 | 2022-02-22
| 8 | Setup and Configuration | 5.4 , 6 | 2022-02-18 | Anindyo |  | 3 | 20 | Not Started | Scope Clarification required | 0% | 2022-03-09 | 2022-03-11
| 9 | LDAP Integration | 5.3 | 2022-02-18 | Anindyo |  | 2 | 21 | Not Started | Next steps: Double confirm + Ensure iBM have the URL for the AD esp since we are in UAT Environment | 0% | 2022-03-11 | 2022-03-14
| 10 | Setup Data Quality Rules | 8 | 2022-02-18 | Ronny |  | 2 | 23 | Not Started |  | 0% | 2022-03-15 | 2022-03-16
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | 11 | Data Source Integration | [5 empty] | 20 |  |  |  | 2022-03-08 | 2022-03-13 |  | 6
| 11.1 | Teradata integration | 5.3 | 2022-02-25 | Son |  | 3 | 20 | Not Started |  | 0% | 2022-03-09 | 2022-03-11 |  | 3
| 11.2 | Oracle integration | 5.3 | 2022-02-25 | Son |  | 3 | 20 | Not Started |  | 0% | 2022-03-09 | 2022-03-11 |  | 3
| 11.3 | SQL Server intgeration | 5.3 | 2022-02-25 | Son |  | 3 | 20 | Not Started |  | 0% | 2022-03-09 | 2022-03-11
| 11.4 | Qlik integration | 5.3 | 2022-02-25 | Manta - Shane |  | 1 | 18 | Not Started | Risk: Need to double confirm & require additional assessment from IBM (to OCBC) | 0% | 2022-03-09 | 2022-03-09
| 11.5 | SAS integration | 5.3 | 2022-02-25 | Manta - Shane |  | 2 | 19 | Not Started |  | 0% | 2022-03-09 | 2022-03-10
| 11.6 | DCT file conversion | 5.3 | 2022-02-25 | Yongjia |  | 1 |  | On-Track | The task as started as of 14th Feb 2022, and Pending reply from OCBC if the current format is aligned and E2E integration to be completed. | 0% | 2022-03-08 | 2022-03-08
| 11.7 | Data Collection Template Integration | 5.3 | 2022-02-25 | Anindyo |  | 3 | 20 | Not Started |  | 0% | 2022-03-09 | 2022-03-11
| 11.8 | Hive integration | 5.3 | 2022-02-25 | Paul |  | 2 | 19 | Not Started |  | 0% | 2022-03-09 | 2022-03-10
| 11.9 | HDFS Integration | 5.3 | 2022-02-25 | Paul |  | 2 | 19 | Not Started | KW will reach out to Arun, Yongjia will be helping to set up in replicate IBM environment | 0% | 2022-03-09 | 2022-03-10
| 11.1 | Atlas (Cloudera) integration | 5.3 | 2022-02-25 | Paul |  | 3 | 20 | Not Started | Cloudera installed failed in IBM Env, Anindyo will share with Paul - arun contact | 0% | 2022-03-09 | 2022-03-11
| 11.11 | Data files | 5.3 | 2022-02-25 | Paul |  | 3 | 20 | Not Started |  | 0% | 2022-03-09 | 2022-03-11
| 11.12 | IGC integration + set up | 5.3 | 2022-02-25 | Paul |  | 3 | 20 | Not Started | Note: OCBC will not providing IGC in POC environment / Paul will share with Anindyo for hard-disk download | 0% | 2022-03-09 | 2022-03-11
```` | 11.13 | Kafka integration | 5.3 | 2022-02-25 | Anindyo |  | 5 | 20 | Not Started |  | 0% | 2022-03-09 | 2022-03-13 |  | 5
| 11.14 | *Kafka Set-up | 5.3 | 2022-02-25 | Anindyo |  | 1 | 18 | Not Started | CE has provided to Anindyo the Kafka set up // pending the machine from Anindyo | 0% | 2022-03-09 | 2022-03-09
| 11.15 | *PowerBI Integration | 5.3 | 2022-02-25 | Manta - Shane |  |  |  | Not Started | Anindyo/Clement will check back on the progress // PowerBI on-prem require additional effort, PowerBI on Azure is fine // Not sure if Manta do support PowerBI > there is gap and clement will escalate | 0% | 2022-03-09 | 2022-03-08
| 11.16 | Manta Support | 11.4 - 11.5 | 2022-02-25 | Manta - Shane |  | 3 | 20 | Not Started |  | 0% | 2022-03-10 | 2022-03-12
Sample phase title block | 12 | Business Metadata capture using GUI |  |  | Son |  |  | 24 |  |  |  | 2022-03-14 | 2022-03-17 |  | 4
| 12.1 | a) Classifications, Categories, Data Classes, Business Terms | 8 |  | Son |  | 3 | 24 | Not Started |  | 0% | 2022-03-14 | 2022-03-17 |  | 4
| 12.2 | b) Custom | 8 |  | Son |  | 3 | 24 | Not Started |  | 0% | 2022-03-14 | 2022-03-17 |  | 4
| 13 | Business Metadata capture using API |  |  | Anindyo |  |  | 24 |  |  |  | 2022-03-11 | 2022-03-17 |  | 7
| 13.1 | a) Classifications, Categories, Data Classes, Business Terms | 5.3 |  | Anindyo |  | 3 | 20 | Not Started |  | 0% | 2022-03-11 | 2022-03-13 |  | 3
| 13.2 | b) Custom | 8 |  | Anindyo |  | 3 | 24 | Not Started |  | 0% | 2022-03-14 | 2022-03-17 |  | 4
Sample phase title block | 14 | Technical Metadata capture using GUI | [5 empty] | 25 |  |  |  | 2022-03-18 | 2022-03-20 |  | 3
| 14.1 | Pre-req: Communicate with Jacob to provide the sample data-set & provide the ORACLE DB INSTANCE | 1 |  | Anindyo |  |  |  | Completed | Request: Anindyo will help provide the Oracle database instance to WL and Arief (10/2) - Anindyo has requested for help from support but pending | 100% | 2022-02-14 | 2022-02-14
| 14.2 | a) Tables, Columns, Databases, Views, Schemas | 10-12.2 |  | Son |  | 3 | 25 | Not Started |  | 0% | 2022-03-18 | 2022-03-20 |  | 3
| 14.3 | b) Stored Procedures, Embedded SQLs, | 10-12.2 |  | Manta - Shane |  | 1 | 25 | Not Started |  | 0% | 2022-03-18 | 2022-03-18 |  | 1
| 14.4 | d) Custom | 10-12.2 |  | Wei Lian / Arief |  | 3 | 25 | Not Started |  | 0% | 2022-03-18 | 2022-03-20 |  | 3
| 15 | Technical Metadata capture using API | [5 empty] | 32 |  |  |  | 2022-03-18 | 2022-03-29
| 15.1 | a) Tables, Columns, Databases, Views, Schemas | 10-12.2 |  | Anindyo |  | 3 | 25 | Not Started |  | 0% | 2022-03-18 | 2022-03-20
| 15.2 | b) Stored Procedures, Embedded SQLs, | 10-12.2 |  | Manta - Shane |  | 1 | 25 | Not Started |  | 0% | 2022-03-18 | 2022-03-18
| 15.3 | c) Dynamic SQLs | 10-12.2 |  | Wei Lian / Arief / Manta - Shane |  | 10 | 32 | Not Started |  | 0% | 2022-03-18 | 2022-03-29
| 15.4 | d) Custom | 10-12.2 |  | Anindyo |  | 5 | 29 | Not Started |  | 0% | 2022-03-18 | 2022-03-24
| 16 | Generate Data profile | 12,14 |  | Son |  | 2 | 27 | Not Started |  | 0% | 2022-03-21 | 2022-03-22
| 17 | Generate Data Lineage | [5 empty] | 33 |  |  |  | 2022-02-14 | 2022-04-01
| 17.1 | General - Qlik, ETL, Stored Procedures, BTQmain, Teradata, SQL Server etc. | 12,14 |  | Manta - Shane |  | 5 | 30 | Not Started |  | 0% | 2022-03-21 | 2022-03-25
| 17.2 | Klook |  | 2022-02-25 | Yongjia |  | 5 | 5 | Not Started | Note: Require validation from OCBC before testing, hence, the dates are not including the alignment session | 0% | 2022-02-14 | 2022-02-18
| 17.3 | Dynamic SQL |  |  | Manta - Shane / Wei Lian / Arief |  | 15 | 18 | Not Started | Risk: Uncertain about the scope and fulfil within timeline | 0% | 2022-02-14 | 2022-03-11
| 17.4 | Run through the final integration between mantas and WKC |  |  | Susanna - WKC owner / Clement |  |  |  | On-Track | Pre-req: Clement has given Susanna a heads up (setting up, dry-run, actual walk-through) | 0% | 2022-03-14 | 2022-03-18
| 17.5 | Evaluation Functionality Coverage (Validate) |  |  | All |  | 5 | 35 | Not Started | Dry-run & Collaborating with Jacob + feedback | 0% | 2022-03-26 | 2022-04-01
| 19 | Walkthrough | 17 | [8 empty] | 2022-04-04 | 2022-04-04 |  | 1
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule.
DO WE NEED ROS HERE? WL NEED TO GET HIS FEEDBACK > DYNAMIC SQL - MEETING ON THURSDAY WITH WL/ARIEF
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As of 26 jan, OCBC still preparing the environment. Tentative: 3rd Feb Reply: As of 4th Feb, the tentative start date is 8th Feb Reply: As of 9th Feb, OCBC environment is ready for us but we need the dropbox access. This will determine the tentative start date.
Note on I6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: the cumulative (total) man-day required to complete this task from the start of the project
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to confirm the Effort day, and the Start + End date for the first stream of work
Note on M64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Critical Path: Task 5 (CP4D Install) Task 8 > Task 12 and Task 14

## Risk log (hidden)
S/N | Environment/Scope | Assumptions/Risk | Date | Owner (if applicable) | Any corrective action? (if applicable) | Overall Status | Impact on our Timeline
1 | OCBC Environment - Data Profiling | Harddisk file transfer is an issue and delayed longer than expected IBM Team faced issues conducting file transfer successfully in OCBC sit as it is slow/failing - YMAL (RHOCP) installation has issues and Lumeng from OCBC has helped addressed it | 2022-02-16 | Anindyo/John/OCBC | As of 23rd feb, All file transfer have been completed but there were many dependencies on OCBC Team. We needed to complete the transfer to the final server that IBM team require to start the installation. However, Muttu have not replied on the progress to OCBC Vivek and IBM Team since he is sick on 22nd-23rd feb. This issue has been highlighted as a dependency for the project since 16th Feb. | Completed | This has delayed our timeline by 1 week
2 | OCBC Environment - Data Profiling | Unable to continue with Part A: Data Profiling due to the OCBC Environmental challenges in our OCP Installation - Nothing can proceed such as CP4D installation till this is completed | 2022-02-23 | Hung/John | Hung and John has already reached out to the OCBC / Redhat personnel to help with troubleshooting of the OCP Installation | Completed | We are unable to start any stream of work under Data Profiling especially when CP4D Installation require substantial time to complete. With our current estimates, the Data profiling workstream will only be completed in the week of 15-18th March which exceed the hard deadline for the demo with OCBC on 14th March.
3 | OCBC Environment - Data Profiling | Terminal provided by OCBC is not working for Weilian when he head down to check on OCBC environment for lineage testing | 2022-03-04 | Weilian/OCBC | Shared the concern with Jacob as of 4th March and 7th March morning at 11am, and raised the ticket to Vivek/Srimathi but no resolution till now. As of 7th March, Wei Lian is using Jacob’s terminal to execute his Dynamic SQL lineage in OCBC environment. This task is completed as of 8th March. | Not Applicable | We are unable to start any stream of work under Data Profiling especially when CP4D Installation require substantial time to complete. With our current estimates, the Data profiling workstream will only be completed in the week of 15-18th March which exceed the hard deadline for the demo with OCBC on 14th March.
4 | IBM internal Environment - Data Lineage and DCT | IGC to WKC integration – unable to find a solution as there is an issue of syncing it up | 2022-02-25 | Anindyo/Clement/Son | Anindyo has reached out to Wilson, but did not revert back any useful insights as he is not aware of this process. - Clement has reached out to Susanne but pending feedback. We will present without the entire lineage flow for non-data assets (e.g. powerbi/qilkview) and share with OCBC that this will be covered as part of WKC V4.5 roadmap which will be part of the implementation plan. | Not Applicable | OCBC has mentioned repeatedly that this is a crucial piece of work that they would like to see in the demonstration.
5 | IBM internal Environment - Data Lineage and DCT | Collaboration with MANTA | 2022-02-28 | IBM/MANTA | As of 2nd March, we have escalated to MANTA that we need a dedicated resource to commit on this POC with us. We have scheduled a daily 9pm SGT call with MANTA to get their updates since week of 24th Feb. With 4th March 9pm-11pm call with MANTA, it helped to set expectation with MANTA in which task that require their immediate attention (E2E Lineage flow) in the next couple of days and we will continue our discuss later in the evening at 9pm. As of 7th March 9-11pm call with MANTA, it has shown that MANTA is not fully committed in sharing the responsibility of Part B: Harvesting Lineage component because.. MANTA require extensive and clear instruction from IBM team before they can execute the task. However, the amount of time required from IBM team to map out the specifics with clear instruction is significant while pursuing the other action items required. MANTA can only share the sample/example of certain activity, and expect IBM team to replicate and complete it when they are suppose to own this task. Especially since IBM does not have the expertise in their solution. | In-progress | Depending on when MANTA can revert back, it is crucial that we close all items by today/tomorrow as majority of our key task need to be completed by this week before our dry run on 9th March.
6 | IBM internal Environment - Data Lineage and DCT | IGC standalone installation and set up | 2022-02-25 | Anindyo/Paul | Anindyo/Son has jumped into a call with Ross to get his time in the next few days to get his inputs and his commitment. With Ross input, Anindyo will assist Paul to take charge in IGC set up by creating the import/output functionality in standalone IGC | Completed

## Project Schedule (wip) (hidden)
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  | UOB ML Ops RFP | [9 empty] | 2023-05-15
Enter Company Name in cell B2. | [10 empty] | Today: | 2023-07-14
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  | WORK IN PROGRESS | [8 empty] | Project Start: | 2023-05-15
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | [10 empty] | Display Week: | 1 |  |  |  | 2023-05-15 | [6 empty] | 2023-05-22 | [6 empty] | 2023-05-29 | [6 empty] | 2023-06-05 | [6 empty] | 2023-06-12 | [6 empty] | 2023-06-19 | [6 empty] | 2023-06-26 | [6 empty] | 2023-07-03 | [6 empty] | 2023-07-10
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2023-05-15 to 2023-07-16
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | S/N | TASK | DEPENDENCIES | ASSIGNED TO | EFFORT | ADDITIONAL DAYS REQ | OCBC ENV- STATUS | IBM ENV - STATUS | COMMENTS | PROGRESS | END/EXPECTED COMPLETION DATE | START | END |  | DAYS | time axis 2023-05-15 to 2023-07-16
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule. | bar: 2023-06-23; 2023-07-05
| A | IGC to WKC (Within CP4D) Sync up |  |  |  |  | Not Applicable | Not Applicable |  | 0% |  | 2022-01-18 | 2022-01-18
• Communicate resized infrastructure requirements to UOB • Communicate EDAG cluster load
| B | Dropbox access (file 8.6 gb) |  |  | 2 |  | Not Applicable | Not Applicable |  | 0% |  | 2023-05-15 | 2023-05-16
| C | Harddisk access |  |  | 2 | 5 | Not Applicable | Not Applicable |  | 0% |  | 2023-05-15 | 2023-05-23 | 2023-05-15 | 2023-05-15
| 1 | Env readiness (VMs) |  |  |  |  | Not Applicable | Not Applicable |  | 0% |  | 2023-05-15 | 2023-05-15
| 1.1 | OCP Pre-requsitie (Domain name and Network) |  |  | 1 |  | Not Applicable | Not Applicable |  | 0% |  | 2023-05-15 | 2023-05-15
| 1.2 | OCP installation (Redhat) |  |  | 1 |  | Not Applicable | Not Applicable |  | 0% |  | 2023-05-15 | 2023-05-15
| 2 | Trial License |  |  | 3 |  | Not Applicable | Not Applicable |  | 0% |  | 2023-05-15 | 2023-05-17
| 3 | Download binaries to local repo |  |  | 3 |  | Not Applicable | Not Applicable |  | 0% |  | 2022-01-14 | 2022-01-18
| 4 | OpenShift install | 1,2,3,C |  | 5 | 1 | Not Applicable | Not Applicable |  | 0% |  | 2023-05-24 | 2023-05-31
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | 5 | CP4D Install | 4 |  | 5 |  | Not Applicable | Not Applicable |  | 0% |  | 2023-06-01 | 2023-06-07 |  | 7
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 5.1 | a) Verify environment | 4 |  |  |  | Not Applicable | Not Applicable |  | 0% |  | 2023-06-01 | 2023-06-07 |  | 7
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | 5.2 | b) Copy binaries to Private Registry | 4 |  |  |  | Not Applicable | Not Applicable |  | 0% |  | 2023-06-01 | 2023-06-07 |  | 7
| 5.3 | c) Foundation steps | 4 |  |  |  | Not Applicable | Not Applicable |  | 0% |  | 2023-06-01 | 2023-06-07 |  | 7
| 5.4 | d) Install required services | 4 |  |  |  | Not Applicable | Not Applicable |  | 0% |  | 2023-06-01 | 2023-06-07 |  | 7
| 6 | Manta Install | 1,2,3 |  | 3 |  | Not Applicable | Not Applicable |  | 0% |  | 2023-05-24 | 2023-05-31
| 7 | Manta integration | 6 |  | 2 |  | Not Applicable | Not Applicable |  | 0% |  | 2023-06-01 | 2023-06-02
| 8 | Setup and Configuration (MANTA) | 5.4 , 6 |  | 3 |  | Not Applicable | Not Applicable |  | 0% |  | 2023-06-08 | 2023-06-10
| 9 | LDAP Integration | 5.3 |  | 2 |  | Not Applicable | Not Applicable |  | 0% |  | 2023-06-08 | 2023-06-09
| 10 | Testing in IBM E2E Integration Environment (Lineage function) |  |  |  |  | Not Applicable | Pending |  | 0% | 2022-03-08 | 2022-02-18 | 2022-03-09
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | 11 | Part A: Data Source Integration | [9 empty] | 2022-02-22 | 2022-03-04 |  | 11
| 11.1 | Teradata integration (Subsitute Db2) | 5.3, 6 |  | 3 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-04 | 2022-02-22 | 2022-03-04 |  | 11
| 11.2 | Oracle integration | 5.3, 6 |  | 3 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-04 | 2022-02-22 | 2022-03-04 |  | 11
| 11.3 | SQL Server intgeration | 5.3, 6 |  | 3 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-04 | 2022-02-22 | 2022-03-04
| 11.4 | Datalake integration (Hive) | 5.3 |  | 3 | 2 | Not Applicable | Not Applicable |  | 0% | 2022-03-07 | 2022-02-22 | 2022-03-04
Sample phase title block | 12 | Part A: Business Metadata config using GUI and API | [9 empty] | 2022-03-04 | 2022-03-08 |  | 5
| 12.1 | a) Classifications, Categories, Data Classes, Business Terms |  |  | 3 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-04 | 2022-03-04 | 2022-03-08 |  | 5
| 12.2 | b) CDE and Glossary DCT |  |  | 3 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-08 | 2022-03-04 | 2022-03-08 |  | 5
Sample phase title block | 13 | Part A: Technical Metadata capture and Data Profiling | [9 empty] | 2022-03-04 | 2022-03-08 |  | 5
| 13.1 | a) Tables, Columns, Databases, Views, Schemas |  |  | 3 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-04 | 2022-03-04 | 2022-03-08 |  | 5
| 13.2 | b) Data Profiling |  |  | 3 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-08 | 2022-03-04 | 2022-03-08 |  | 5
| 13.3 | c) Data Quality |  |  | 3 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-08 | 2022-03-07 | 2022-03-09 |  | 3
| 14 | Demonstration prep work |  |  | 2 |  | Not Applicable | Not Started |  |  | 2022-03-09 | 2022-03-09 | 2022-03-10
| 14.1 | Part B: Harvesting Lineage | [8 empty] | 2022-02-21 | 2022-02-18 | 2022-03-08
| 14.2 | Oracle |  |  | 8 | 4 | Not Applicable | Not Applicable |  | 0% | 2022-03-09 | 2022-02-22 | 2022-03-08
| 14.3 | SQL |  |  | 8 | 4 | Not Applicable | Not Applicable |  | 0% | 2022-03-09 | 2022-02-22 | 2022-03-08
| 14.4 | Teradata (Subsitute Db2) |  |  | 8 | 4 | Not Applicable | Not Applicable |  | 0% | 2022-03-09 | 2022-02-22 | 2022-03-08
| 14.5 | Datalake (Hive) |  |  | 8 | 4 | Not Applicable | Not Applicable |  | 0% | 2022-03-08 | 2022-02-22 | 2022-03-08
| 14.6 | Atlas |  |  |  |  | Not Applicable | Not Applicable |  | 0%
| 14.6 | Qilkview to MANTA |  |  | 8 | 4 | Not Applicable | Not Applicable |  | 0% | 2022-03-08 | 2022-02-22 | 2022-03-08
| 14.7 | MANTA to IGC (ORACLE, MSSQL, POWERBI) Export archive zip |  |  |  |  | Not Applicable | Not Applicable |  | 0% | 2022-03-08 | 2022-02-22 | 2022-02-24
| 14.8 | PowerBI |  |  | 8 | 3 | Not Applicable | Not Applicable |  | 0% | 2022-03-09 | 2022-02-22 | 2022-03-06
| 14.9 | Dynamic SQL |  |  | 14 | 1 | Not Applicable | Not Applicable |  | 0% | 2022-03-08 | 2022-02-18 | 2022-03-08
| 14.1 | IGC to WKC (Within CP4D) Sync up |  |  | 8 |  | Not Applicable | Not Applicable
| 14.11 | Klook to MANTA |  |  | 14 | 1 | Not Applicable | Not Applicable |  | 0% | 2022-03-08 | 2022-02-18 | 2022-03-08
| 14.12 | OPEN MANTA - IGC (Qilkview and Klook) |  |  |  |  | Not Applicable | Not Applicable |  | 0% | 2022-03-09
| 14.13 | Kafka integration |  |  | 8 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-09 | 2022-02-22 | 2022-03-03
| 14.14 | Standalone IGC (Import and Export) |  |  | 2 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-08 | 2022-03-03 | 2022-03-08
| 15 | Part B: DCT Loading and Stiching | [9 empty] | 2022-02-22 | 2022-03-07
| 15.1 | DCT Template (E2E Lineage) |  |  | 8 | 4 | Not Applicable | Not Applicable |  | 0% | 2022-03-09 | 2022-02-22 | 2022-03-07
| 15.2 | DCT Integration |  |  | 8 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-09 | 2022-02-22 | 2022-03-03 |  | 10
| 15.3 | E: Other features (Governance workflow and and audit tracking) |  |  |  |  | Not Applicable | Not Applicable |  |  | 2022-03-14
This is an empty row | 16 | Walkthrough | [9 empty] | 2022-03-08 | 2022-03-10 | 3/14/24 | 3/14/25
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | 16.1 | Demo Prep Work |  |  | 1 |  | Not Applicable | Not Applicable |  | 0% | 2022-03-10 | 2022-03-08 | 2022-03-09 |  | 2
|  | Final Presentation / Playback |  |  |  |  | Not Applicable | Not Applicable |  | 0% | 2022-03-10 | 2022-03-09 | 2022-03-10
|  | Walkthrough | [9 empty] | 2022-03-14 | 2022-03-14
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As of 26 jan, OCBC still preparing the environment. Tentative: 3rd Feb Reply: As of 4th Feb, the tentative start date is 8th Feb Reply: As of 9th Feb, OCBC environment is ready for us but we need the dropbox access. This will determine the tentative start date.
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to confirm the Effort day, and the Start + End date for the first stream of work
Note on C27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (double check with Son)

## Working Sheet (hidden)
Questions | Answers
Timeline | 12th june - Start of Installation / 26th June - Start of PoC
When is the end date? | 14th July - end of POC (UOB ask: 3-weeks to complete)
What is the timeline given by client and how we are planning to achieve within this timeline? | Nigel mentioned that it is planned for 14th June for installation
Where are we in the current timeline? What is on-track, pending, completed etc?
Evaluation criteria:
I understand we have the evaluation criteria by Functional vs Technical. Have we mapped out according to two category: 1. Yes / No - whether we can meet this criteria with use-case, product demo, presentation? | For all 5 use-case, we are not possible to showcase the 200+ evaluation criteria - using uOB data and models.
2. How are we going to demonstrate that we meet this criteria? If nil, what are we planning to do to cover the gap? | For those that we are unable to cover in the 5 use-case, we will cover in iBM environment.
3. Who is going to own/drive it? | Clear disconnect between paltform owner vs business users - business users who are giving the use-case.
Functional criteria mapping will be shared by Nigesh EOD , Sunny should be IC in Technical criteria + driving it
Role and Responsibilities
1. Who are we coordinating with UOB?
CE Team: Nigesh Eddy AG (+ Tianhuat) | Unclear whether Tianhaut into the PoC / we should not include Tianhuat as a resource for POC
Sunny - clarify if the laptop comes with the badge
Assets / Depositories
1. Share the working box folder and materials | Nigel - initiate PM (infra) | we need a POC / representative from this Business unit - we do not have an official point of contact for each business use-case
2. Where is all the material sent by the client? | Abishek - Taken over functional PM (functional) | We have not received it
Danny PM - send questions
1st June - meeting with UOB
Additional blocker / news from Legal | In the next timeline schedule, lets have a org chart +
Functional use-case | Technical
Nijesh | Sunny
AG | Tan Long Siau - storage
Eddy | Hung - installation
Prasad (risk of not being part of the PoC) | John - installation
Tianhuat (risk of not being part of the PoC) | Jordan
> highly dependant on the qualification call for Starhub
> clarity from Starhub - whether to pivot towards Plan A / Plan B | Remote support:
China Labs - will remotely present the specialised requirement
Next steps: | What I need?
1. Create the UPDATED timeline schedule and ALIGN with the client - Abishek - the schedule should be important and at least towards the end of next week and they can plan their availabilities | I need the evaluation criteria by: 1. Who is doing it? 2. How we going to demonstrate it? In the Client environment: use-case / product demo or IBM environment or presentation 3. Timeline 4. Intended audience / persona for the demo session | I need the pre-requsitie both IBM and UOB for each session:
2. Dedicated sheet on the UPDATED timeline schedule aligned with each responsibilities
3. Risk and potential blockers - with mitigation plan
4. Guided tour / documentation for each day demo - including the PoC evaluation criteria checklist has been met at the end of the presentation
5. After all the demo completed, we should have a session to PoC summary conclusion and validation with the BU

## Tracking Admin (hidden)
S/N | Topic | Open Items | Expected Completion Date | Owner | Next steps or Corrective actions? | Overall Status
1 | Project Mangement - Timeline | Consolidated internal timeline overlaid with both Nijesh inputs (from Functional evaluation criteria) and Sunny inputs (Technical evaluation criteria) with the view on the following points: - Covered within the use-case – in the client environment? If no, it will be covered in IBM environment and demonstrated by CE - Out of the box vs Custom? – which I understand if it is out-of-the-box demo, Presales team will demonstrate it - Specific Owner - Timeline / Date of completion - Pre-requisite to achieve each use-case / criteria | 2023-06-12 | Nijesh, Sunny |  | Completed
2 | Project Mangement - Timeline | Finalised client-view timeline with essential information only: 1. Track of activities 2. Applicable use-case 3. Intended Audience 4. Scoring Criteria Reference 5. Timeline - specifically which are the dates where we need the face-to-face interaction with the client to showcase the demo | 2023-06-13 | Nijesh, Sunny, Vavarly |  | Completed
3 | Project Mangement - Timeline | As part of the timeline schedule, we should also consider the following: 1. Socialisation session with UOB stakeholders to conclude the PoC and validate if we have met all criteria so far – this should happen after all the hands-on demo and before the “CP4D” roadmap 2. Preparation of guided tour / documentation for each day of the hands-on session need to be considered in the timeline | 2023-06-13 | Vavarly, Sunny |  | In-Progress
4 | Project Mangement - Governance and Structure | Create a team org chart, and introduce the finalised timeline with the org chart. In addition, formally introduce Vavarly (As the POC) so that all client communication should come through me. | 2023-06-13 | Vavarly, Sunny |  | In-Progress
5 | Project Mangement - Risk Mitigation Plan | Nijesh mentioned that he is preparing the initial view for the list of potential risks / issues with a mitigation plan. He will share it with the extended team so that we can flag and highlight risk early. E.g. Resource / Environment / Infrastructure risks | 2023-06-13 | Nijesh |  | In-Progress
6 | [5 empty] | In-Progress
7 | [5 empty] | In-Progress
8 | [5 empty] | In-Progress
9 | [5 empty] | In-Progress
10 | [5 empty] | In-Progress
11 | [5 empty] | In-Progress
12 | [5 empty] | In-Progress
13 | [5 empty] | In-Progress

## Risk mitigation plan (hidden)
S/N | Topic | Open Risk items | Implication | Expected Completion Date | Owner | Next steps or Corrective actions? | Overall Status
1 | PoC Legal Agreement | POC agreement from UOB as there are couple of things that our legal team do not agree | Timeline will be delayed till it is sorted out |  | Wai Leng |  | In-Progress
2 | Software Evaluation License | Software Evaluation portal - software evaluation license - Colin & Puru direction is that we have the POC agreement from UOB then the eval license is fine as long as its for non-production but we need valid confirmation from the client | Timeline will be delayed till it is sorted out |  | Wai Leng |  | In-Progress
3 | CP4D Installation | UOB planned to allocate a shared SIT cluster for this POC, which has been used by other application as well ( OpenShift cluster with 7 Worker Node configuration ) . - They will share 5 /7 worker node for IBM cloud Pak for data installation. IBM cloud pak for data will be installed in the 3 name spaces and labelled to use the assigned nodes. - CP4D software downloaded from icr.io with full license keys. However during install we will use the Trial license key accepted by UOB team. - Uninstallation may need to be planned carefully , since installation will copy the images to catalogue sources which are common to overall cluster. | Shared SIT Cluster which is not ideal since we are unclear of the implication when there is any impact in other application running in this cluster. |  | Wai Leng, John |  | Not Started
4 | [6 empty] | Not Started
5 | [6 empty] | Not Started
7 | [6 empty] | Not Started
8 | [6 empty] | Not Started

## Pending items (hidden)
S/N | Topic | Open items | Expected Completion Date | Owner | Next steps or Corrective actions? | Overall Status
1 | Laptop collection | Sunny is coordinating and managing the UOB Laptop collection for all 7 laptops. There is locker for us to store the laptop. Sunny has also shared a confidential mail of their user and password to each colleague. |  | Sunny | Pending for each user to confirm and validate their own laptop. | Completed
2 | IBM Environment set up | Sunny and Eddy is setting up the Techzone cluster for this POC. Pending information on what are the requirements / items required to be communicated to UOB team. E.g. we are hoping to limit to 5 users etc |  | Sunny | Pending the information to be provided to UOB team | Pending
3 | User role mapping | Abishek has shared his initial draft and POV of the role-user mapping. Nijesh has validated it. |  | Nijesh |  | In-Progress
4 | Use-case packages | Pending from UOB team. Shared only 2 out of 5 packages so far. Importantly, please provide the list of dependencies for the list of packages - scripts for the remaining three Business Units. |  | Abishek / Nigel / Lucy |  | Completed
5 | Model Artifacts | Premise based on the aforementioned call : · IBM team will only onboard the scripts and models(if at all applicable) on to the platform and will demonstrate all the possible points as mentioned in the POC scoring criteria. · Python scripts used to connect to data sources. · Python scripts used to transform, feature engineer and build the model. · Any miscellaneous scripts required to run the aforesaid scripts. Why do we need 5 working days before the showcase to perform the following actions for all the five use cases: · As explained earlier as well we need the week to do the following : · Onboard all the assets on to the platform. · Test the data connection and prepare the dependencies for the user scripts. · Add orchestration and other features from IBM CP4D to the existing assets. · Prepare the No Code/Low Code flows for the relevant use cases. · Add deployment and monitoring component to the workflow. · Ensure and test the end to end MLOps and governance workflow on CP4D hosted in the UOB POC environment. |  | Abishek / Nigel / Lucy | Pending any feedback from Abishek | In-Progress
6 | User role mapping | Please provide the list of users with their personas. |  | Abishek |  | Pending
7 | Clarification questions | Please reply to all the clarification questions attached the excel sheet for your reference. |  | Abishek / Nigel |  | Completed
8 |  | Could you update us about the outcome of “Potential Consolidation” column in the schedule. |  | Abishek |  | Completed
9 | OpenShift | OpenShift Parameters Configuration |  | Lucy |  | Pending
10 | OpenShift | OpenShift StorageClass is not compatible with IBM CP4D pre-requisite |  | Lucy |  | Completed

## Timeline - Schedule
S/N | Stage | Activity | Status | Days Required | Timeline | Timeline (Planned) | Timeline(Acutal) | Predecessor | Dependency and Help required from UOB Team
| Preparation for Installation | IBM Software Images delivery to UOB | Completed | 1
| Preparation for Installation | Infra setup validation by IBM (sanity check) | Completed | 1
| Preparation for Installation | Images transferred to destination (USB - > UOB Laptop - > Server - > JFrog) | Completed | 3
1 | Installation of CP4D in UOB Environment | Cloud Pak for Data Installation 1. Verify environment 2 Copy (or download) binaries to Private Registry - completed 3. Foundation steps - completed 4. Install required services - completed | In-Progress | 2 | 6/7 - 7/7 | 6/7 - 7/7 | 6/7 - 14/7 |  | UOB team to provide the network connectivity for the following: 1. Connectivity from bastion node to OCP (to run scripts) 2. Connectivity from Jfrog to OCP (to pull images) In order to do step 3/4: 1. We need DevOps team to log in the credentials 2. UOB OCP Team need to generate the token and share with us 3. Support during installation from DevOps and OCP team 4. We need get access to the permanent Bastion node with connectivity to OCP and private registry - port is still in progress but the Bastion node is available 5. Physical access to the building is required (especially on the weekend) 6. Putty terminal access installed in the assigned laptop (currently, Zaoyi is sharing with us since the assigned laptop does not have access.)
2 | LDAP Configuration | 1. IBM to provide details of LDAP requirement to UOB - completed 2. IBM to configure CP4D on LDAP configuration | Pending from UOB | 1 | 2023-07-08 | 2023-07-10 | 10/7/2023-14/7/2023 | 1 | 1.UOB to provide the LDAP configuration details 2. UOB to support IBM during the configuration (Contact person required for support) 3. Physical access to the building is required (especially on the weekend) 4. Putty terminal access installed in the assigned laptop (currently, Zaoyi is sharing with us since the assigned laptop does not have access.)
3 | Cloudera Configuration (Hive, Impala, HDFS) | 1. IBM to provide details of Cloudera requirement to UOB - completed 2. IBM to configure CP4D on Cloudera configuration | Pending from UOB |  | 2023-07-08 | 2023-07-10 | 10/7/2023-14/7/2023 | 1 | 1.UOB to provide the Cloudera configuration details 2.UOB to support IBM during the configuration (Contact person required for support) 3. UOB to provide the data sources for testing purpose - In the data connectivity for Hive, the data prepared for front-shell detection need to be available for testing. 4. Physical access to the building is required (especially on the weekend) 5. Putty terminal access installed in the assigned laptop (currently, Zaoyi is sharing with us since the assigned laptop does not have access and we would need access over the weekend)
4 | Python package / Conda Configuration | IBM to configure CP4D / OCP on Python package / Conda Configuration | Completed | 3 | 8/7 - 10/7 | 10/7 - 12/7 | 10/7 - 12/7 | 1 | 1. UOB to provide the Jfrog and Python repository details 2. UOB to support IBM during the configuration (Contact person required for Jfrog) and OCP support 3. Physical access to the building is required (especially on the weekend)
5 | Preparation for the Showcase | 1. Onboard all the assets 2. Test all the services installed on the platform (end-to-end flow) 3. Prepare all the necessary documentation, assets and flow required during the use-case showcase | In-Progress |  | 8/7 - 10/7 | 10/7 - 12/7 | 11/7 - 14/7 | 1,4 (Ideally, 2+3) | Same as "Cloudera Configuration (Hive, Impala, HDFS)" and "Python package / Conda Configuration" dependencies stated above. Physical access to the building is required (especially on the weekend)
6 | Showcase | 15 Show-case cutting across 11/7 - 26/7 for best case scenario | Not Started |  | 11/7 - 26/7 |  | 17/7 - 3/8 | 1,2,3,4,5 | Dependency on 1-5

## Showcase Dates
Stage | Date | Environment | Scoring Criteria Reference | Overlaps | Activity
Projects and Data Access | 2023-07-17 | UOB Environment | Functional criteria - A 1.1A - A 3.5 - A 4.1.4 - A 4.2.9 - A 4.2.10 | Technical Criteria: - B1.1.13 - B1.3.2 - B1.3.3 (6) - B1.3.5 | 1. Create project 2. Add collaborator 3. Create environment 4. Create job 5. Create data connections to data source (show Teradata as well) (note: dependancy on the outcome of the connectivity workstream) 6. Test connection 7. Model Runtimes and Customisation 8. Create 5 catalogs for each BU. Add roles (DS, DE, BA).
Custom Data Access | 2023-07-17 | UOB Environment |  | Technical Criteria: - B1.7.8 - B1.3.16 - B1.3.3 (3) - B1.3.6 - B1.3.7 -B1.3.11 -B1.3.12 | 1. Create Data Protection Rule (DS cannot view NRIC (eg)) 2. Data Virtualisation using Watson Query (shift to 2 August) 4. Ad-hoc CSV file upload in catalog.
Data Transformation,Visualization | 2023-07-17 | UOB Environment | Functional criteria - A 1.1 B - A 1.1 C | Technical Criteria: - B1.2.2 - B1.2.3 - B1.2.4 - B1.3.17 - B1.3.3 (2) - B1.4.1 | 1. Data Transformation using Modeler Flow. 2. Data Profiling and visualization. 3. Save the dataset
Model Development and Feature Engineering | 18/7/23 - 19/7/23 | UOB Environment | Functional criteria - A 1.2 - A 1.3 | Technical Criteria - B1.2.2 | 1. Create notebook 2. Port scripts/notebooks to Watson Studio 3. Link notebook to environment 4. Run notebook 5. Push the features to feature store. 6. Feature discovery and resuability
AutoAI | 20/7/23 - 21/7/23 | UOB Environment | Functional criteria - A1.4A.25 - A1.4A.26 - A1.4A.28 - A1.4A.29 - A1.4A.30 - A1.4A.31 - A1.4A.32 - A1.4A.33 - A1.4A.34 |  | 1. Create AutoAI pipeline 2. Build model using step 1 leveraging data connection 3. Generate notebook 4. Save model
Model Training Custom Demos | 2023-07-24 | IBM Environment | Functional criteria - A1.4A - A1.4B - A1.4C |  | 1. Unstructured Data Processing 2. Ensemble learning Methods 3. Decision Optimisation 4. Modelling using Structured with techniques like Reinforcement learning, Supervised Learning , GAN, Time Series Modelling etc 5. Training Models on GPU
Deployment and Monitoring | 25/7/23 - 26/7/23 | UOB Environment | Functional criteria - A2.1 - A2.2 - A2.3 - A3.4 | Technical Criteria: B1.2.1 (Batch API) | 1. Push models to model registry 2. Push AutoAI models to WML 3. Deploy as online and batch models 4. Configure OpenScale through UI and run monitoring 5. Show notebook for model deployment to WML and OpenScale | OpenScale Impact
Pipelines and Experiment Tracking | 2023-07-27 | UOB Environment | Functional criteria - A2.3- Experiment Tracking - A2.1.5 - A3.3 | Technical Criteria - B1.2.1 (sync API) - B1.2.5 - B1.2.6 - B1.2.7 - B1.2.8 - B1.2.9 - B1.2.10 - B1.4.5 - B1.6.1 - B1.6.4 | 1. Introduce Watson Studio Pipeline 2. Create dev pipeline (link notebooks) 3. Create job and run pipeline for deployment 4. Track Experiments using pipeline and Factsheets. 5. Track model using Factsheets. 6. Debugging and troubleshooting Pipelines 7. Is it possible to show one failed pipeline with logs? 8. Is it possible to show a notification of job success via email
CI Testing and Pre-Prod Pipeline | 2023-07-28 | IBM Environment | Functional criteria - A2.1.6 - A2.2 |  | 1. Write CI tests (basics) 2. Create pre-production pipeline and monitor model using OpenScale
CI/CD Integration | 2023-07-28 | IBM Environment | Functional criteria - A2.1.6 - A2.2 - A3.4 - A4.2.11 - A4.2.12 | Technical Criteria - B1.5.1 (2,3) - B1.5.2 - B1.5.5 - B1.5.8 | 1. Configure Jenkins for CI/CD integration 2. Configure Github for CI/CD integration and PR approvals 3. Use Jenkins and CI test to push model to pre-production and model registry
Custom Deployment Demos | 2023-07-31 | IBM Environment | Functional criteria - A2.1 - A2.2 | Technical Criteria - B1.2.7 | 1. Ease of integrating / import of external models 2. Model rollbacks 3. Model Exchange formats
Model Governance & Responsible AI | 2023-07-01 | UOB Environment | Functional criteria - A3.1 - A3.2 | Technical Criteria: B1.6.2 | 1. Promote model in OpenScale 2. Integrate Veritas toolkit with OpenScale 3. Compute Fairness, Drift, Feature importance using SHAP and LIME etc. 4. Bias detection and Mitigation 5. Run prod pipeline 6. Approve model using OpenPages workflow
Model Retirement | 2023-08-01 | UOB Environment | Functional criteria - A2.4 |  | 1. Retrain model 2. Retire model
CP4D Administration and Audit Trail | 2023-08-01 | IBM Environment | Functional criteria - A3.6 - A4.2 | Technical Criteria - B1.1.12 - B1.2.11 - B1.2.12 - B1.6.5 - B1.6.6 - B1.6.7 - B1.7.1 - B1.7.2 - B1.7.4 - B1.10 (a) - B1.10 (b) - B1.10 (c) - B1.10 (d) | 1. Monitoring of resources like CPU and Memory (capacity utlization) and generation of alerts 2. Tracking of actions by users 3. Multinenacy 4. LDAP Integration: AAD/Kerberos 5. Restart services 6. API documentation Since API has been removed from the POC criteria, we would replace this with scalability 7. Backup (housekeeping) - presentation
Data Virtualization | 2023-08-02 | • Plan A: UOB Environment - depending on outcome of connectivity to Cloudera • Contingency Plan: Showcase in IBM environment with the same proposal sent earlier. |  |  | •. Data Virtualization (Virtualize, govern, query)
CPD4.7 and Roadmap features/products | 2023-08-02 | IBM Environment |  |  | 1. Introduce feature group 2. VS Code Extension Demo 3. Generative AI and Large Language Models. 4. Conduct Q&A

## BTS
Custom Data Access | 2023-07-17 | UOB Environment
1. Create Data Protection Rule |  | Sunny
2. Ad-hoc CSV file upload in catalog. |  | Sunny

## WIP (hidden)
As of: 26 June 2023
Stage | S/N | Activity | Applicable Use Case | Status | Dependencies | Number of Tracks | Potential Consolidation | Intended Audience | Scoring Criteria Reference | Overlaps | Nature of the guided session for UOB | Remarks | 2023-06-12 | 2023-06-13 | 2023-06-14 | 2023-06-15 | 2023-06-16 | 2023-06-17 | 2023-06-18 | 2023-06-19 | 2023-06-20 | 2023-06-21 | 2023-06-22 | 2023-06-23 | 2023-06-24 | 2023-06-25 | 2023-06-26 | 2023-06-27 | 2023-06-28 | 2023-06-29 | 2023-06-30 | 2023-07-01 | 2023-07-02 | 2023-07-03 | 2023-07-04 | 2023-07-05 | 2023-07-06 | 2023-07-07 | 2023-07-08 | 2023-07-09 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-13 | 2023-07-14 | 2023-07-15 | 2023-07-16 | 2023-07-17 | 2023-07-18 | 2023-07-19 | 2023-07-20 | 2023-07-21 | 2023-07-22 | 2023-07-23 | 2023-07-24 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-28
Preparation | 1.1 | Call with DevOps/Infra on installation questions |  | Completed |  |  |  | UOB DevOps/Infra team |  |  |  |  | 1st round complete |  | 2nd round scheduled
| 1.2 | Presentation of schedule | NA | Completed |  | NA |  | UOB user groups and project managers |  |  |  |  | Completed |  |  | Clarified questions from Abishek and Nigel
| 1.3 | POC Legal Agreement |  | Completed | [7 empty] | Acknowledge as of 22nd June
| 1.4 | Software Evaluation License |  | Completed | [7 empty] | Acknowledge as of 22nd June
| 1.5 | LOU Agreement |  | Completed | [7 empty] | Acknowledge as of 23rd June
| 1.6 | UOB to provide IBM with list of packages needed for all the five use cases (2 out of 5 received) | NA | Completed | 1.3 and 1.4 | NA |  | Usecase Owners from UOB |  |  |  | We are aligned with UOB Team that we are only going to focus on 1 use-case for majority of our show-case |  |  |  |  | `
| 1.7 | UOB to provide IBM with Data, Models and Artifacts | NA | Completed | 1.3 and 1.4 | NA |  | Usecase Owners from UOB |  |  |  | As od 20/6, UOB Abishek shared that the use case / data set to use for preparation of showcase – he is still getting that aligned with the users and will revert - Model & Artifacts: The users expect to create the models on the platform during their hands on - Data: The data is prepared by users and will be provisioned on > Cloudera – To source into MAP > Data to be provisioned into MAP (SAS data set & images for working with unstructured data) – this would be made available when the installation is commenced
| 1.8 | IBM to provide installation images to UOB via HDD | NA | Completed | 1.3 and 1.4 | NA | [5 empty] | IBM Software Images delivery to UOB – 26 June [Completed] Infra setup validation by IBM (sanity check) – 26 June [Completed]
| 1.9 | UOB to upload installation images in Bastion node | NA | Completed | 1.3 and 1.4 | NA | [5 empty] | Images transferred to destination (USB - > UOB Laptop - > Server - > JFrog) – 26 June to 28 June [In Progress]
| 1.10' | OpenShift Cluster, NFS Storage, Jfrog Artifactory with 500 GB storage, Bastion node (as indicated in BOM and architecture) | NA | Completed | 1.3 and 1.4 | NA | [24 empty] | Completed
Cloud Pak for Data Installation in UOB environment | 2.1 | Cloud Pak for Data Installation 1. Verify environment 2 Copy (or download) binaries to Private Registry 3. Foundation steps .4. Install required services 5. Kerberos keytabs (source?) & Integration with UOB LDAP - user and role setup for MAP application | NA | Pending from UOB | 1.3, 1.4, 1.7, 1.8 and 1.9 | NA |  | NA | [27 empty] | Best Case | Best Case | Best Case
Set up and configured a CP4D cluster in IBM Environment ( TechZone ) | 2.2 | 1. Set up and confirgure a CP4D cluster in IBM environment - Techzone 2. Set up the 5 user ID for UOB users to access and view the demo assets 3. Validate if the 5 user ID to access and view the demo assets | NA | Completed | 1.3, 1.4, 1.7, 1.8 and 1.9 | [6 empty] | Eddy has shared that we have successfully set up and configured a CP4D cluster in IBM Environment which is TechZone. | [18 empty] | Completed
2.3
Preparation for the Showcase | 3 | 1. Onboard all the assets 2. Test all the services installed on the platform (end-to-end flow) 3. Prepare all the necessary documentation, assets and flow required during the use-case showcase | NA | Not Started | 1.7, 1.8, 1.9 and 2.1
Projects and Data Access | 4 | 1. Create project 2. Add collaborator 3. Create environment 4. Create job 5. Create data connections to data source (show Teradata as well) 6. Test connection 7. Model Runtimes and Customisation 8. Create 5 catalogs for each BU. Add roles (DS, DE, BA). | FX - next best action Return over asset Shell detection Digital wealth acquisition Credit card acquisition | Not Started | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Data Engineers 3. Data/Business Analysts 4. Business Users | Functional criteria - A 1.1A - A 3.5 - A 4.1.4 - A 4.2.9 - A 4.2.10 | Technical Criteria: - B1.1.13 - B1.3.2 - B1.3.3 (6) - B1.3.5 | Face2Face
Custom Data Access | 5 | 1. Create Data Protection Rule (DS cannot view NRIC (eg)) 2. Create data connections to additional data sources like Teradata etc. 3. Data Virtualisation using Watson Query (Demostrating federation on the UOB environment for PoC) 4. Ad-hoc CSV file upload in catalog. | IBM Environment | In-Progress | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Data Engineers 3. Data/Business Analysts 4. Business Users |  | Technical Criteria: - B1.7.8 - B1.3.16 - B1.3.3 (3) - B1.3.6 - B1.3.7 -B1.3.11 -B1.3.12
Data Transformation,Visualization | 6 | 1. Data Transformation using Modeler Flow. 2. Data Profiling and visualization. 3. Save the dataset | FX - next best action Return over asset Shell detection Digital wealth acquisition Credit card acquisition | Not Started | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Data/Business Analysts 3. Business Users | Functional criteria - A 1.1 B - A 1.1 C | Technical Criteria: - B1.2.2 - B1.2.3 - B1.2.4 - B1.3.17 - B1.3.3 (2) - B1.4.1 | Face2Face
Model Development and Feature Engineering | 7 | 1. Create notebook 2. Port scripts/notebooks to Watson Studio 3. Link notebook to environment 4. Run notebook 5. Push the features to feature store. 6. Feature discovery and resuability | FX - next best action Return over asset Shell detection Digital wealth acquisition Credit card acquisition | Not Started | 1.7, 1.8, 1.9 and 2.0 | 5 | Possible | 1. Data Scientists 2. Data Engineers 3. Data/Business Analysts | Functional criteria - A 1.2 - A 1.3 | Technical Criteria - B1.2.2 | Face2Face
AutoAI | 8 | 1. Create AutoAI pipeline 2. Build model using step 1 leveraging data connection 3. Generate notebook 4. Save model | FX - next best action Shell detection Digital wealth acquisition Credit card acquisition | Not Started | 1.7, 1.8, 1.9 and 2.0 | 4 | Possible | 1. Data Scientists 2. Data/Business Analysts 3. Business Users | Functional criteria - A1.4A.25 - A1.4A.26 - A1.4A.28 - A1.4A.29 - A1.4A.30 - A1.4A.31 - A1.4A.32 - A1.4A.33 - A1.4A.34 |  | Face2Face | This section on AutoAI will not be applicable to return over asset use case
Model Training Custom Demos | 9 | 1. Unstructured Data Processing 2. Ensemble learning Methods 3. Decision Optimisation 4. Modelling using Structured with techniques like Reinforcement learning, Supervised Learning , GAN, Time Series Modelling etc 5. Training Models on GPU | IBM Environment | In-Progress | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Data Engineers 3. Data/Business Analysts | Functional criteria - A1.4A - A1.4B - A1.4C |  | Face2Face/Online
Deployment and Monitoring | 10 | 1. Push models to model registry 2. Push AutoAI models to WML 3. Deploy as online and batch models 4. Configure OpenScale through UI and run monitoring 5. Show notebook for model deployment to WML and OpenScale | FX - next best action Return over asset Shell detection Digital wealth acquisition Credit card acquisition | Not Started | 1.7, 1.8, 1.9 and 2.0 | 5 | Possible | 1. Data Scientists 2. Data Engineers 3. Data/Business Analysts 4. Business Users | Functional criteria - A2.1 - A2.2 - A2.3 - A3.4 | Technical Criteria: B1.2.1 (Batch API) | Face2Face | Model monitoring will not be applicable to return over asset use case but model deployment will be applicable
Pipelines and Experiment Tracking | 11 | 1. Introduce Watson Studio Pipeline 2. Create dev pipeline (link notebooks) 3. Create job and run pipeline for deployment 4. Track Experiments using pipeline and Factsheets. 5. Track model using Factsheets. 6. Debugging and troubleshooting Pipelines 7. Is it possible to show one failed pipeline with logs? 8. Is it possible to show a notification of job success via email | Selected Usecase | Not Started | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Data/Business Analysts 3. Data Engineers | Functional criteria - A2.3- Experiment Tracking - A2.1.5 - A3.3 | Technical Criteria - B1.2.1 (sync API) - B1.2.5 - B1.2.6 - B1.2.7 - B1.2.8 - B1.2.9 - B1.2.10 - B1.4.5 - B1.6.1 - B1.6.4 | Face2Face
CI Testing and Pre-Prod Pipeline | 12 | 1. Write CI tests (basics) 2. Create pre-production pipeline and monitor model using OpenScale | IBM Environment | In-Progress | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Data Engineers 3. Data/Business Analysts 4. Business Users | Functional criteria - A2.1.6 - A2.2 |  | Face2Face | Model monitoring will not be applicable to return over asset use case but model deployment will be applicable
CI/CD Integration | 13 | 1. Configure Jenkins for CI/CD integration 2. Configure Github for CI/CD integration and PR approvals 3. Use Jenkins and CI test to push model to pre-production and model registry | IBM Environment | In-Progress | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Data Engineers 3. Data/Business Analysts 4. Software/DevOps Engineers | Functional criteria - A2.1.6 - A2.2 - A3.4 - A4.2.11 - A4.2.12 | Technical Criteria - B1.5.1 (2,3) - B1.5.2 - B1.5.5 - B1.5.8 | Face2Face | As per the communication on 15th June with Abhishek and Nigel, its best suited to be demonstrated on IBM Environment.
Custom Deployment Demos | 14 | 1. Ease of integrating / import of external models 2. Model rollbacks 3. Model Exchange formats | IBM Environment | In-Progress | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Data/Business Analysts 3. Data Engineers | Functional criteria - A2.1 - A2.2 | Technical Criteria - B1.2.7 | Face2Face
Model Governance & Responsible AI | 15 | 1. Promote model in OpenScale 2. Integrate Veritas toolkit with OpenScale 3. Compute Fairness, Drift, Feature importance using SHAP and LIME etc. 4. Bias detection and Mitigation 5. Run prod pipeline 6. Approve model using OpenPages workflow | Selected Usecase | Not Started | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Model Auditors/Validators 3. Data/Business Analysts 4. Software/DevOps Engineers | Functional criteria - A3.1 - A3.2 | Technical Criteria: B1.6.2 | Face2Face
Model Retirement | 16 | 1. Retrain model 2. Retire model | Selected Usecase | Not Started | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Model Auditors/Validators 3. Data/Business Analysts 4. Software/DevOps Engineers | Functional criteria - A2.4 |  | Face2Face | Model retraining will not be applicable for return over asset use case but model retirement will be applicable
CP4D Administration and Audit Trail | 17 | 1. Monitoring of resources like CPU and Memory (capacity utlization) and generation of alerts 2. Tracking of actions by users 3. Multinenacy 4. LDAP Integration: AAD/Kerberos 5. Restart services 6. API documentation 7. Backup (housekeeping) - presentation | NA | Not Started | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. IT Operations Engineers | Functional criteria - A3.6 - A4.2 | Technical Criteria - B1.1.12 - B1.2.11 - B1.2.12 - B1.6.5 - B1.6.6 - B1.6.7 - B1.7.1 - B1.7.2 - B1.7.4 - B1.10 (a) - B1.10 (b) - B1.10 (c) - B1.10 (d) | Face2Face/Online
CPD4.7 and Roadmap features/products | 18 | 1. Introduce feature group 2. VS Code Extension Demo 3. Generative AI and Large Language Models. 4. Conduct Q&A | IBM Environment | Not Started | 1.7, 1.8, 1.9 and 2.0 | 1 |  | 1. Data Scientists 2. Data Engineers 3. Data/Business Analysts 4. Software/DevOps Engineers 5. Business Users |  |  | Face2Face/Online

## Technical criteria align (hidden)
Which activities? | S/N | Description | RFP response | Questions for UOB/Remarks | How to demonstrate | Tech Sales/Support needed
| B1.1 | Architecture
CP4D Administration and Audit Trail | B1.1.12 | How do you support single instance multi tenancy where the different tenants could comprise different business units in the Bank across different countries. | Yes, the proposed solution supports mutli-tenancy in a single installation.Refer to link https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=architecture-multitenancy-support for details on out of the box multi-tenancy support. |  | ANUP: Project and deployment space | Anup
| B1.1.13 | Ability to support single centralized repository for all models and policy related objects with partitioning based on user groups | Yes The proposed solution includes centralized repository for all models and policy related objects with role based access control granted based on user's membership of appropriate user group. The link provides further details on Watson Knowledge Catalog which provides this functionality. https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=governance-catalogs | "Policy" means? | 1. Store/Share assets (including models) - Catalog (provided by WKC). 2. Deploy assets (including models) - Deployment Space (provided by WML) |  | Tech Sales/
| B1.2 | Integration Capabilities |  |  |  |  | Demonstrated through functional
| B1.2.1 | Provide a list of interfaces methods the platform can ingest data from external system, e.g. batch, sync API call, async APIs via streaming | The proposed solution has out of the box support for Spark and APIs which allows integration to external systems, with support for batch, sync API call, async APIs | "Ingest" means "access"? The proposed platform doesn't include any data repository | Notebook/Spark Job/Notebook Job | China team with spark | Information/presentation
| B1.2.2 | Batch: Ability to generate data files to be used by downstream systems in different formats: fixed length text, CSV, SAS, XML | The proposed solution can generate data files in different formats such as : fixed length text, CSV, XML etc. (Minor effort) | Will show CSV | Notebook/Data Refinary/SPSS Flow | CE Team | Non compliant item/ those which UOB stated not required will not be demonstrated
| B1.2.3 | Batch: Ability to customize the content and format of input and output interface files | The proposed solution can be customized to generate content and format of input and output files. (Minor effort) | Please clarify what is meant by interface files and provide an example | file or database - wml batch connection | CE Team - Notebook with Python can help to detect the format of the file? | Open or need support
| B1.2.4 | Batch: Ability to customize interface files content and format within the product UI without development effort | The proposed solution user interface can used customized to generate content and format of input and output files. (Minor effort) | Please clarify what is meant by interface files and provide an example | file or database - wml batch connection | CE Team - Notebook with Python can help to detect the format of the file?
| B1.2.5 | Batch: Ability to use built-in scheduler to schedule batch jobs based on | The proposed solution includes scheduler to schedule batch jobs. | Pipelines? Or https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=assets-creating-deployment-job Creating jobs in deployment spaces A job is a way of running a batch deployment, or a self-contained asset like a script, notebook, code package, or flow in Watson Machine Learning. You can select input and output for your job and choose to run it manually or on a schedule. From a deployment space, you can create, schedule, run, and manage jobs. | pipeline
| B1.2.6 | a. recurring on date/time/cycle | The proposed solution includes scheduler to schedule batch jobs recurreing on date/time/cycle. | Pipelines? Or https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=assets-creating-deployment-job Creating jobs in deployment spaces A job is a way of running a batch deployment, or a self-contained asset like a script, notebook, code package, or flow in Watson Machine Learning. You can select input and output for your job and choose to run it manually or on a schedule. From a deployment space, you can create, schedule, run, and manage jobs. | pipeline | upto a minute level
| B1.2.7 | b. ad-hoc execution of certain batch job | The proposed solution includes scheduler to schedule adhoc batch jobs. | Pipelines? Or https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=assets-creating-deployment-job ibm.comibm.com Creating jobs in deployment spaces A job is a way of running a batch deployment, or a self-contained asset like a script, notebook, code | pipeline
| B1.2.8 | c. certain predefined trigger: i.e. utilisation exceeds certain threshold | The proposed solution includes scheduler that can generate an alert based on pre-defined parameter. | Pipelines? Or https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=assets-creating-deployment-job Creating jobs in deployment spaces A job is a way of running a batch deployment, or a self-contained asset like a script, notebook, code | pipeline | Ask Nijesh
| B1.2.9 | d. dependency between jobs, e.g. start the job as soon as another job is finished and successful | The proposed solution includes Watson pipelines that can be used to establish run of of the batch jobs, based on the dependency. |  | pipeline
| B1.2.10 | Batch: Ability to define batch job schedule and trigger by end users without developer effort | The proposed solution includes Watson pipelines that can be used to establish run of of the batch jobs. |  | pipeline
| B1.2.11 | API: provide documents for APIs available on the platform out-of-box | Refer to link https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=resources-available-apis | information provided during RFP | Presentation - downloaded file in API tool and show (safari) | Watson Data API
| B1.2.12 | API: please provide API protocol (e.g. SOAP, REST, gRPC, Kafka, MQ) and access control details | Refer to link https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=resources-available-apis | information provided during RFP | Presentation | Kafka, MQ, Supported, GRPC?
| B1.2.13 | API: Ability to customize input parameter and output payload for APIs | The proposed solution can be customised to inut parameter and outout payload of the APIs. Refer to link https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=resources-available-apis | API Payload - you mean for Machine Learning model scoring using API Call? | WML Rest API - same as above real time | Ask Nijesh
| B1.2.14 | API: ability to customize APIs by end-user within the UI without developer effort | Non compliant | Non compliant items will not be demonstrated
| B1.2.15 | API: Ability to trace API calls and display output in UI to assist monitoring and troubleshooting | The proposed solution includes the monitoring console which allows viewing API acitivity in the UI to assist in monitoring and troubleshootong |  |  | Develop control mode? Ask Nijesh
| B1.2.16 | API: Ability for streaming APIs (if any) to support Apache Kafka as the transport layer | The proposed soluition supports Apache Kafka connection that can be configured for use as transport layer. Refer to link https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=catalogs-apache-kafka-connection | How and in what use case will Kafka be provided | Demonstrate connection to Kafka using platform connection
| B1.2.17 | Ability to import and execute existing score card models from other vendor's software, e.g. SAS | The proposed solution can import models from other vendor's software such as SAS using PMML. Refer to link https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=specifications-supported-frameworks-software | Please provide SAS models in PMML format. | Add model from Cp4d project | CE Team - Any dummy PMML-format SAS model that we can use for demo purpose?
| B1.2.18 | Ability to integrate with web services and MQ/EAI to perform data enrichment for real time offers | Proposed solution provides ability to integrate with web services and MQ/EAI. | What exactly will be required to be demonstrated |  | Ask Nijesh
| B1.2.19 | Ability to provide support for industry standard based Application Performance Management and integration with common 3rd party APM tools (CA APM, Geneos, App Dynamics etc.) | https://docs.broadcom.com/doc/ca-application-performance-management-for-openshift https://docs.itrsgroup.com/docs/all/compatibility-matrix/geneos/compat-matrix.htm#Containe https://www.appdynamics.com/solutions/openshift | We will not be demonstrating integration with APM tools | We will not be demonstrating integration with APM tools as we are using existing UOB Openshift cluster. We are assuming this cluster has been integrated. (As indicated by UOB)
| B1.3 | Datasources
| B1.3.1 | Provide list of data sources (e.g. RDBMS, NoSQL DB, Cloud Storage, SAS, Hive, HDFS) with version which the platform can support to ingest data into the platform | Refer to link: https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=data-supported-sources | Information provided during RFP. In the use cases, connections specified are Hive, SAS, Impala, and Parquet files | Presentation
| B1.3.2 | Ability to integrate with source data without requiring significant ETL work by developers. Please elaborate scenarios where development work is required for data ingestion into the platform | The proposed solution includes tools for integrating with source data for developers without requiring significant ETL work. In the event there is a need for ETL, it is assumed that the solution will leverage the bank's existing ETL tools and processes |  | Data Virtualization/Data Refinary/SPSS Flow | CE Team - can you help to demonstrate this using SPSS Flow?
| B1.3.3 | Ability to ingest data from different systems internal or external to the bank that uses the following protocols:
|  | 1. Teradata | The proposed soluton provides ability to connect to Teradata using out of the box connector. https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=catalogs-teradata-connection . | In the use cases, connections specified are Hive, SAS, Impala, and Parquet files | Show Platform Connection
|  | 2. Flat files of various format: CSV, XML, JSON, fixed length | The proposed solution suopports ingestion of data from flat files. https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=data-supported-sources |  | SPSS Flow for CSV, XML. | CE Team - can SPSS Flow supports Fixed length & JSON?
|  | 3. Flat files of various encoding: e.g. UTF8, ASCII, EBCDIC, Thai (TIS620) | The proposed solution includes Watson Query which is capable of automatically detects the encoding scheme of flat data files, such as CSV and TSV files. https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=connectors-setting-character-encoding-scheme and list of supported encodings are listed at the link https://docs.oracle.com/javase/8/docs/technotes/guides/intl/encoding.doc.html |  | DV using Remote Connectors
|  | 4. PDF files, e.g. credit bureau reports. Information needs to be extracted from PDF and parsed for ingestion | The proposed solution can accomplish this through python scripting in Watson Studio | How does this tie in to the 5 use cases
|  | 5. SAS dataset | The proposed solution can accomplish this through python scripting in Watson Studio. Please refer link - https://blogs.sas.com/content/sasdummy/2017/04/08/python-to-sas-saspy/ | Bank will provide SAS dataset | SPSS Flow/ Data Refinery | CE Team - SPSS Flow can access SAS Asset? https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=data-supported-sources
|  | 6. HIVE/Implala | The proposed soluton provides ability to connect to Hive using out of the box connector.https://www.ibm.com/docs/en/SSQNUZ_4.6.x/wsj/manage-data/conn-hadoop-hive.html | Can the bank provide the Hive/Impala source? Is it keberos-enabled cluster? https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=catalogs-apache-hive-connection | Platform Connection
|  | 7. RDBMS Databases - Oracles, DB2, SQL, Postgresql, MariaDB |  | Information provided during RFP. In the use cases, connections specified are Hive, SAS, Impala, and Parquet files | Platform Connection
| B1.3.4 | Ability to ingest only changed data for various data sources | The proposed solution assumes that change data capabilites needed for the Data Platform is available in the bank's Data Platform (EDAG) and will leverage it. IBM does have Change Data Capture solution to meet the requirements, however, based on the above assumption, it is not proposed (non compliant) | Change data capture has not been proposed as part of the solution
| B1.3.5 | Effort and timelines to set up a new connectivity for any of the above |  |  | Platform Connection
| B1.3.6 | Ability to run customized queries to get data from the data sources | The proposed solution can be configured to run customized query to get data from data sources. |  | Watson Query | Sunny
| B1.3.7 | Ability to Support Federated/Unified Query to access the data from multiple data sources like DB2, Hive or Teradata | The proposed solution can use Watson Query to access data from multiple sources. Refer to link https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=services-watson-query | Information provided during RFP. In the use cases, connections specified are Hive, SAS, Impala, and Parquet files | Watson Query | Sunny
| B1.3.8 | Ability to support impersonation for Kerberos based authentication for datasource connection | Refer to link: https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=considerations-kerberos-authentication | Which sourse? We currenlty supports Hive/Impala/Hbase/HDFS/Kafka for Keberos-based authentication | Platform Connection | https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=catalogs-apache-hive-connection
| B1.3.9 | Ability to support preparation of different types of data (e.g. Transaction, Accounts & Customer), please describe the process | The proposed solution is capable of connecting to data sources that contain different types of data (e.g. Transaction, Accounts and customer.) Refer to link https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=data-supported-sources. The exact process to be adopted for the data preparation is to be determined in close consulation with Bank during the implementation. | Is this related to the 5 use cases? Please provide more details on the scenario.
| B1.3.10 | supports storage of inputs, derived fields & results (including score weight per score drivers for scorecard) to other databases such as SQL, Oracle, Teradata etc. | The proposed solution can be customized to have an extensible data model which allows for elements to be added and customised to the specific requirements of the bank during the implementation in close consultation with the Bank. Depending upon the selection of the data repository, limitation on the number of fields and tables can be determined during the development of such data model. (Noted) |  | Batch scoring against data in some databases SPSS Modeler Flow
| B1.3.11 | Ability to query multiple data sources at the same time when designing a strategy/policy (design time) | This can be accomplished by Watson Query which uses Data Virtualization |  | Platform Connection Watson Query | Sunny
| B1.3.12 | Ability to query multiple data sources at the same time when executing a strategy/policy (run time) | This can be accomplished by Watson Query which uses Data Virtualization |  | Platform Connection Watson Query | Sunny
| B1.3.16 | Ability to allow ad-hoc data upload inot the platform by end users. Please elobrate on types of data allowed and formats supported (i.e. customer data in CSV format) | Assuming the end-user has been granted appropriate access |  | File upload. Type of files will depend on the components https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=data-supported-sources
| B1.3.17 | Ability to perform data validation during data ingestion. Please elaborate on the process and mechanism | Validation of the data during ingestion will be performed by banks existing data ingestion tools (Noted) | As responses during the RFP, validation of the data during ingestion will be performed by bank's internal validation tools | Basic data validation can be done using WKC Profiling Tab https://www.ibm.com/docs/en/SSQNUZ_4.6.x/wsj/getting-started/profile.html | Sunny
| B1.3.18 | Able to process large-volume data a) Could the platform work with large, raw data directly (e.g. transactional data, digital data), without the need for pre-processing and/or aggregation? b) Please elaborate what situation /scenarios that require pre-aggregated info before ingestion for platform computation | Pre-processing of the data during ingestion will be performed by banks existing data ingestion tools (Noted) | As stated in clarification responses, We originially did not size for the 1 TB load testing of the system in the infrastructure sizing, so we cannot guarantee that this will work effectively. We are currently considering some techniques and performing internal testing to validate whether this can be performed in the POC. | IBM Analytics Engine | Sunny - is it the right response from the RFP? CE Team - can you help with question (b)
| B1.3.19 | Supports storage of inputs, derived fields & results (including score weight per score drivers for scorecard) to other databases such as SQL, Oracle, Teradata etc. | The proposed solution can write to SQL, Oracle, Teradata using out of the box connections | Which use case requires writing to SQL, Oracle, & Teradata | Batch scoring against data in some databases SPSS Modeler Flow | Show connectors
| B1.4 | Integration with Delivery Platforms
| B1.4.1 | Ability to generate files that contains the result of policy execution for the downstream system to consume. The following format and encoding should be supported: UTF8, ASCII Fixed length, CSV, XML, JSON | All these formats can be supported by Watson Knowledge Catalog | Does this mean that out of the five use cases, the output would be generated in these formats? | SPSS Flow
| B1.4.2 | After interface files are generated, automatically invoke file transfer mechanism to send the file to the destination server via the following protocols: FTP, Secure FTP (SFTP), MQ/TDE | Partially compliant | This would require additional components not part of proposed solution
| B1.4.3 | Ability to expose REST and SOAP API to invoke execution of policy on certain customers/accounts. Please provide APIs that are available out-of-box and describe the API security mechanisms | What is interface file in the context of this requirement. SOAP not supported. Partially compliant | What is interface file in the context of this requirement. SOAP not supported. Partially compliant" | Online Deployment with WML. Security: https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=functions-authenticating
| B1.4.5 | Ability to capture feedback from downstream system in order to form a closed information loop e.g. the platform calculate a temp limit increase for a customer, send the recommendation to credit card system, later when the temp limit is utilied (or not utilized), the platform will capture the feedback from the downstream system and store the result inside the platform for 12 months | Fully compliant but need more details | Need more details | OpenSCale/pipeline | CE Team - can you help to demonstrate this? Verbally explain during pipelines?
| B1.5 | Development, Testing, DevOps
| B1.5.1 | Provide details of the DevOps CI/CD support in terms of tools and processes used during deployment. Does the the Supplier have the ability to support the following tooling:
|  | 2. Environment Setup/Deploy - Puppet, Jenkins, Kubernetes | The oroposed solution will be able to use the tools provided by the bank with some basic training on the usage. All environment provisioning is operator-drived unsing cpd-cli operators. These are either initiated at the command line, in restful invocatons, or with the administration GUI. (Minor effort required) | We are proposing to show this in an IBM envronment with Jenkins |  | CE Team - can you help to demonstrate this?
|  | 3. SCM / Build / Binary control - Git/Bitbucket, Artifactory, Maven, Gradle | (RFP response- Partially Compliant- Minor Effort ) The oroposed solution will be able to use the tools provided by the bank with some basic training on the usage. This is a requirement at all our clients, and can best be demonstrated as part of model lifcycle management. May not cover all the SCM's that UoB have. | We are proposing to show this in an IBM envronment and focus on Git/BitBucket |  | CE Team - can you help to demonstrate this?
| B1.5.2 | Provide describe product out-of-box capability to integrate with CI/CD tool chain. Please provide detailed example of end-to-end loop of dev, deploy, test workflow | Partially compliant and Minor effort required | We are proposing to show this in an IBM envronment with Jenkins |  | CE Team - can you help to demonstrate this?
| B1.5.5 | Ability to perform the promotion using Export & Import feature between environments | The proposed solution supports this through different deployment spaces for various environments (eg Model Dev, Model Pre-Prod, Mode- Prod) |  | OpenScale, FactSheet | CE Team - can you help to demonstrate this?
| B1.5.8 | Ability to support automated deployment across environments. Please highlight if this is done within the product or requires integration to third party tools and if so, which tools and how are they integrated. | Can be done through different deployment spaces for various environments and integration with CI/CD pipelines (e.g. Jenkins) |  | Not sure how we can demonstrate this? Maybe CP4D Dev -> Git -> CP4D Prod | CE Team and Anup - any idea
| B1.6 | Logging, Monitoring & Alerting
| B1.6.1 | Ability to alert on job failures or hardware/network failures with detailed reason notes on failures, e.g. data source is not accessible, input data file contains data entries that fails validation rules, etc | Alerts on job failures for various services in CP4D is accomplished through Waton pipelines job logs |  | Watson Pipelines | CE
| B1.6.2 | Ability to alert when API invocation failure exceeding certain predefined SLAs | Assuming pre-defined SLAs are referring to drift, fairness, performance metrics, alerts can be raised when there are SLA breaches during scoring APIs (OpenScale) |  | OpenScale | CE
| B1.6.4 | Ability to notify on jobs success with a summary to respective groups | The proposed solution provides this ability through Job notification triggered via email (Pipelines) |  | Watson Pipelines | CE
| B1.6.5 | Ability to monitor and review capacity utilization and report spike in capacity utilization for cloud/on-premise and hybrid deployments | The proposed solution is assumed to be deployed within the Bank's data centre and can monitor capacity utilization and is configurable to generate alerts depending on pre-defined threshholds of resource utilisation. Refer to link https://docs.openshift.com/container-platform/4.10/monitoring/reviewing-monitoring-dashboards.html Of course, deployment to public clouds such as IBM, AWS ,Azure and Google is supported and even in case of the cloud deployment, such resource utilisationc can be monitored and alerts can be generated. |  | OpenShift Console | Anup/John
| B1.6.6 | Ability to support system monitoring, reporting and generation of notification and alerts. | The proposed solution is assumed to be deployed within the Bank's data centre and can monitor capacity utilization and is configurable to generate alerts depending on pre-defined threshholds of resource utilisation. Refer to link https://docs.openshift.com/container-platform/4.10/monitoring/reviewing-monitoring-dashboards.html |  | OpenShift Console | Anup/ John
| B1.6.7 | Ability to support audit logging of user action, e.g. user download of data. Please elaborate on the type of audit trail the platform can capture and and highlight if certain audit trail have negative impact on performance | The proposed solution provides ability capture many audit events as described on the link https://www.ibm.com/docs/en/SSQNUZ_4.6.x/cpd/admin/audit-events.html . Also refer to link for best practices in monitoring the proposed solution: https://www.ibm.com/docs/en/SSQNUZ_4.6.x/cpd/admin/best-practice-monitoring.html |  |  | Anup - any idea how we can do this?
| B1.6.8 | Ability to provide an out of the box, standards based logging capability for all components/events which can be e.g. consumed by aggregation platforms such as Splunk and ELK | The proposed solution can be configured to send logs to external SIEM products such as Splunk. Refer to link https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=environment-exporting-audit-records-siem-solution | This would need forwarding of audit events to any of the following: Splunk QRadar® LogDNA zen-audit pod stdout logs Do we need to demonstrate this? |  | Slide
| B1.7 | Application Security
| B1.7.1 | Ability to support authentication using Bank's Active Directory for user creation, maintenance, and housekeeping of users, assignment to roles and permissions, authorization, including, but not limited to, integration and alignment with the security in EDAG and other data sources. | Refer to link: https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=users-connecting-your-identity-provider | Integration with Active Directly & Kerberos Keytabs required? Do we need to demonstrate this? | LDAP Integration | John/Anup
| B1.7.2 | Ability to perform Auto AD Sync while User ID mapped with User Group Mapping | Refer to link: https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=reference-user-mgmt | Integration with Active Directly & Kerberos Keytabs required? Can you help to explain the requirement 'while User ID mapped with User Group Mapping' ? | Cloud Pak for Data provides two options for syncing with your LDAP server: - Sync on Login - Periodic Sync https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=users-connecting-your-identity-provider | John/Anup
| B1.7.4 | Ability to support Multiple AD Domains | The proposed solution includes Identity and Access Management Service (IAM Service) which can be used to support multiple AD domains. Refer to link: https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=environment-migrating-your-ldap-configuration-iam-service | Integration with Active Directly & Kerberos Keytabs required? Do we need to demonstrate this? |  | John/Anup
| B1.7.8 | Ability to support fine-grained authorization controls including data access controls e.g. who can or cannot download PII data vs non-PII data, who can access PII vs non-PII data, restricting one Business Unit's (BU) user from accessing another BU's data. | The proposed solution supporst security and access control including segregation of users, groups, roles and their permissions. |  | Data Protection Rule with WKC | CE will create catalogs in first session Sunny with create data protection rule
| B1.7.9 | Ability to log and track data downloads, access, data dissemination across teams and resources for audit purposes
| B1.8 | Deployment
| B1.9 | Platform Support
| B1.10 | IT Usability
|  | a) Restart services and servers (via script and via Ops menu) | The proposed solution canrestart services and servers using script and graphical user interface menu. Refer to link https://docs.openshift.com/container-platform/4.10/virt/virtual_machines/virt-controlling-vm-states.html |  | Services can be shutdown or restarted using CPD CLI https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=resources-shutting-down-restarting-services or restart pods manually using Cp4d console | Anup
|  | b) Generate Audit reports | The proposed solution provides capabilities to view audit logs. Refer to link https://docs.openshift.com/container-platform/4.10/security/audit-log-view.html |  | You can configure IBM Cloud Pak® for Data to forward audit records to a security information and event management (SIEM) solution, such as Splunk, LogDNA, or QRadar. https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=environment-exporting-audit-records-siem-solution | Anup
|  | c) Archival and housekeeping | The proposed solution has capabilites to back up which can be used for archival and housekeeping |  | Presentation by Tan Long | Anup - any idea? - Tang Long
|  | d) Monitoring e.g. by user, user group, task, process, session, CPU/memory/storage utilization (and corresponding alerts and notifications) | Refer to link - https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=platform-monitoring-alerting | Monitoring consol in Cloud Pak for Data | Cp4d monitoring https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=2-monitoring-platform | Sunny
| B1.10.8 | Ability to configure the data retention period for platform | The proposed solution provides capability to configure the data retention period for platform. Refer to link https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=platform-changing-retention-period-monitoring-data | Need to login to OC, connect to Influx DB and change retention policy | Cp4d monitoring https://www.ibm.com/docs/en/cloud-paks/cp-data/4.6.x?topic=2-monitoring-platform | Anup

## Sheet2 (hidden)
Completed
In-Progress
Pending from IBM
Pending from UOB
At-Risk
In-Review
Not Started

## Sheet3 (hidden)
Projects and Data Access | Functional criteria - A 1.1A - A 3.5 - A 4.1.4 - A 4.2.9 - A 4.2.10 | Technical Criteria: - B1.1.13 - B1.3.2 - B1.3.3 (6) - B1.3.5
| A 1.1A | B1.1.13
| A 3.5 | B1.3.2
| A 4.1.4 | B1.3.3 (6)
| A 4.2.9 | B1.3.5
A 4.2.10
Custom Data Access |  | Technical Criteria: - B1.7.8 - B1.3.16 - B1.3.3 (3) - B1.3.6 - B1.3.7
Data Transformation,Visualization | Functional criteria - A 1.1 B - A 1.1 C | Technical Criteria: - B1.2.2 - B1.2.3 - B1.2.4 - B1.3.17 - B1.3.3 (2) - B1.4.1
Model Development and Feature Engineering | Functional criteria - A 1.2 - A 1.3 | Technical Criteria - B1.2.2
AutoAI | Functional criteria - A1.4A.25 - A1.4A.26 - A1.4A.28 - A1.4A.29 - A1.4A.30 - A1.4A.31 - A1.4A.32 - A1.4A.33 - A1.4A.34
Model Training Custom Demos | Functional criteria - A1.4A - A1.4B - A1.4C
Deployment and Monitoring | Functional criteria - A2.1 - A2.2 - A2.3 - A3.4 | Technical Criteria:
Pipelines and Experiment Tracking | Functional criteria - A2.3- Experiment Tracking - A2.1.5 - A3.3 | Technical Criteria - B1.2.5 - B1.2.6 - B1.2.7 - B1.2.8 - B1.2.9 - B1.2.10 - B1.4.5 - B1.6.1 - B1.6.4
CI Testing and Pre-Prod Pipeline | Functional criteria - A2.1.6 - A2.2
CI/CD Integration | Functional criteria - A2.1.6 - A2.2 - A3.4 - A4.2.11 - A4.2.12 | Technical Criteria - B1.5.1 (2,3) - B1.5.2 - B1.5.5 - B1.5.8
Custom Deployment Demos | Functional criteria - A2.1 - A2.2 | Technical Criteria - B1.2.7
Model Governance & Responsible AI | Functional criteria - A3.1 - A3.2 | Technical Criteria: B1.6.2
Model Retirement | Functional criteria - A2.4
CP4D Administration and Audit Trail | Functional criteria - A3.6 - A4.2 | Technical Criteria - B1.1.12 - B1.2.11 - B1.2.12 - B1.6.5 - B1.6.6 - B1.6.7 - B1.7.1 - B1.7.2 - B1.7.4 - B1.10 (a) - B1.10 (b) - B1.10 (c) - B1.10 (d)
CPD4.7 and Roadmap features/products

## Project Schedule (OCBC Env) (hidden)
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  | OCBC Data Lineage RFP - POC | [8 empty] | 2022-02-14
Enter Company Name in cell B2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  | Scope: OCBC Data Lineage RFP includes - Data Profiling | [7 empty] | Project Start: | 2022-02-14
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | [9 empty] | Display Week: | 1 |  |  |  | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-02-14 to 2022-04-17
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | S/N | TASK | DEPENDENCIES | ASSIGNED TO | EFFORT | CUMULATIVE MAN-DAY EFFORT | STATUS | COMMENTS | PROGRESS | END/EXPECTED COMPLETION DATE | START | END |  | DAYS | time axis 2022-02-14 to 2022-04-17
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule. | bar: 2022-03-25; 2022-04-06
| A | Testing in IBM Environment |  | Hung / John / Son |  |  | Completed |  | 100% |  | 2022-01-18 | 2022-01-18
| B | Dropbox access (file 8.6 gb) |  | OCBC / Clement / Anindyo | 2 |  | Completed |  | 100% |  | 2022-02-14 | 2022-02-15
| C | Harddisk access |  | OCBC / Anindyo / John | 7 | 1 | Completed | As of 22nd Feb AM, All the files has been copied to OCBC Environment, the OCBC person was on sick - hopefully by today afternoon it will be completed - installation file to the final machine but this should be completed // Vivek - 23feb morning will start > IBM will go down on-site | 100% | 2022-02-16 | 2022-02-14 | 2022-02-22 | 2022-02-14 | 2022-02-14
| 1 | Env readiness (VMs) |  | OCBC / IBM |  |  | Completed |  | 100% |  | 2022-02-14 | 2022-02-14
| 1.1 | OCP Pre-requsitie (Domain name and Network) |  | Hung / John | 1 | 1 | Completed |  | 100% |  | 2022-02-14 | 2022-02-14
| 1.2 | OCP installation (Redhat) |  | Hung / John | 1 | 1 | Completed |  | 100% |  | 2022-02-14 | 2022-02-14
| 2 | Trial License |  | Clement | 3 | 3 | Completed |  | 100% |  | 2022-02-14 | 2022-02-16
| 3 | Download binaries to local repo |  | Son / Hung | 3 |  | Completed |  | 100% |  | 2022-01-14 | 2022-01-18
| 4 | OpenShift install | 1,2,3,C | John / Hung | 5 |  | On-Track | In progress | 50% | 2022-02-27 | 2022-02-23 | 2022-02-27
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | 5 | CP4D Install | 4 | John | 5 | 8 | On-Track | In progress | 50% | 2022-02-27 | 2022-02-23 | 2022-02-27 |  | 5
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 5.1 | a) Verify environment | 4 | John |  |  | Completed |  | 100% | 2022-02-27 | 2022-02-23 | 2022-02-27 |  | 5
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | 5.2 | b) Copy binaries to Private Registry | 4 | John |  |  | Completed |  | 100% | 2022-02-27 | 2022-02-23 | 2022-02-27 |  | 5
| 5.3 | c) Foundation steps | 4 | John |  |  | Not Started |  | 0% | 2022-02-27 | 2022-02-23 | 2022-02-27 |  | 5
| 5.4 | d) Install required services | 4 | John |  |  | Not Started |  | 0% | 2022-02-27 | 2022-02-23 | 2022-02-27 |  | 5
| 6 | Manta Install | 1,2,3 | Anindyo | 2 | 9 | On-Track | installation is done, but Issue logging in MANTA +. Have reached out Shane and he will troubleshoot it | 80% | 2022-02-27 | 2022-02-23 | 2022-02-24
| 7 | Manta integration | 6 | Anindyo | 2 | 10 | Not Started |  | 0% | 2022-02-27 | 2022-02-25 | 2022-02-26
| 8 | Setup and Configuration (MANTA) | 5.4 , 6 | Anindyo | 3 | 10 | Not Started |  | 0% | 2022-02-27 | 2022-02-25 | 2022-02-27
| 9 | LDAP Integration | 5.3 | Anindyo | 2 | 9 | Not Started |  | 0% | 2022-02-27 | 2022-02-23 | 2022-02-24
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | 10 | Part A: Data Source Integration |  |  |  | 13 |  | Assumption: Complete within a day |  |  | 2022-02-28 | 2022-03-02 |  | 3
| 10.1 | Teradata integration | 5.3 | Son | 3 | 13 | Not Started |  | 0% | 2022-03-06 | 2022-02-28 | 2022-03-02 |  | 3
| 10.2 | Oracle integration | 5.3 | Son | 3 | 13 | Not Started |  | 0% | 2022-03-06 | 2022-02-28 | 2022-03-02 |  | 3
| 10.3 | SQL Server intgeration | 5.3 | Son | 3 | 13 | Not Started |  | 0% | 2022-03-06 | 2022-02-28 | 2022-03-02
| 11.4 | Datalake integration (Hive) |  | Paul | 3 | 13 | Not Started |  | 0% | 2022-03-06 | 2022-02-28 | 2022-03-02
Sample phase title block | 11 | Part A: Business Metadata config using GUI and API |  | Anindyo |  | 13 |  | Assumption - Data Profiling (12-14): Complete by 3-4th march |  |  | 2022-02-28 | 2022-03-02 |  | 3
| 11.1 | a) Classifications, Categories, Data Classes, Business Terms | 8 | Anindyo | 3 | 13 | Not Started |  | 0% | 2022-03-03 | 2022-02-28 | 2022-03-02 |  | 3
| 11.2 | b) CDE and Glossary DCT | 8 | Anindyo/Nas | 3 | 13 | Not Started |  | 0% | 2022-03-03 | 2022-02-28 | 2022-03-02 |  | 3
| 13 | Business Metadata capture using API |  | Anindyo |  | 15 |  |  |  |  | 2022-02-28 | 2022-03-04 |  | 5
| 13.1 | a) Classifications, Categories, Data Classes, Business Terms | 5.3 | Anindyo | 3 | 15 | Not Started |  | 0% | 2022-03-09 | 2022-03-02 | 2022-03-04 |  | 3
| 13.2 | b) Custom | 8 | Anindyo | 3 | 14 | Not Started |  | 0% | 2022-03-09 | 2022-02-28 | 2022-03-03 |  | 4
Sample phase title block | 12 | Part A: Technical Metadata capture and Data Profiling |  |  |  | 17 |  | Start on 1st Mar / Data Profiling should be completed by 3-4 Mar |  |  | 2022-03-03 | 2022-03-08 |  | 6
| 12.1 | a) Tables, Columns, Databases, Views, Schemas |  | Son | 3 | 17 | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-08 |  | 6
| 12.2 | b) Data Profiling |  | Son | 1 | 14 | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-03 |  | 1
| 12.3 | c) Loading the 36 Metadata field |  | Anindyo/Nas | 3 | 17 | Not Started | Completed by 3-4 Mar | 0% | 2022-03-03 | 2022-03-03 | 2022-03-08 |  | 6
| 13 | Part B: Harvesting Lineage
| 13.1 | a) Oracle |  | Son | 3 | 17 | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-08
| 13.2 | b) SQL |  | Son | 1 | 16 | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-07
| 13.3 | c) Teradata |  | Son | 3 | 17 | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-08
| 13.4 | d) Datalake and Atlas |  | Paul ?? | 3 |  | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-08
| 13.5 | e) Qilkview |  | Manta / YJ | 3 |  | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-08
| 13.6 | f) PowerBI |  | Manta / Anindyo | 3 |  | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-08
| 14 | Part B: DCT Loading and Stiching |  |  |  | 17 |  |  |  |  | 2022-03-03 | 2022-03-08
| 14.1 | a) Tables, Columns, Databases, Views, Schemas |  | Anindyo | 3 | 17 | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-08
| 14.2 | b) Stored Procedures, Embedded SQLs, |  | Manta - Shane | 1 | 14 | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-03
| 14.3 | c) Custom |  | Anindyo | 3 | 17 | Not Started |  | 0% | 2022-03-03 | 2022-03-03 | 2022-03-08
| 15 | Walkthrough | [8 empty] | 2022-03-10 | 2022-03-10
| 15.1 | Evaluation Functionality Coverage (Dry-Run) |  | All | 3 |  | Not Started | 10th March Morning 930-1230pm - Dry Run is meant to illustrate everything for actual walkthrough // Susanne will be a separate session | 0% | 2022-03-10 | 2022-03-10 | 2022-03-10
| 16 | Walkthrough | [5 empty] | 14 Mar 2:30pm - 6:30pm |  |  | 2022-03-14 | 2022-03-14 |  | 1
This is an empty row | [12 empty] | 3/14/24 | 3/14/25
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule.
|  | We will keep with his current project plan (Part A and B) and update with the team update | [5 empty] | my webex
slide - presented in RFP presentation > produce the skeleton
topics to discuss > time required for each section > 3.5 hours target to complete
1-2 buffer in between (3:45pm mark)
profiling need to br prioritise > so need to validate with the team
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As of 26 jan, OCBC still preparing the environment. Tentative: 3rd Feb Reply: As of 4th Feb, the tentative start date is 8th Feb Reply: As of 9th Feb, OCBC environment is ready for us but we need the dropbox access. This will determine the tentative start date.
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: the cumulative (total) man-day required to complete this task from the start of the project
Note on L6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to confirm the Effort day, and the Start + End date for the first stream of work

## Project Schedule (Internal Env) (hidden)
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  | OCBC Data Lineage RFP - POC | [8 empty] | 2022-02-14
Enter Company Name in cell B2. | [10 empty] | 2022-02-21 | 2022-02-18
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  | Scope: OCBC Data Lineage RFP includes - Data Lineage | [7 empty] | Project Start: | 2022-02-14
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | [9 empty] | Display Week: | 1 |  |  |  | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-02-14 to 2022-04-17
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | S/N | TASK | DEPENDENCIES | ASSIGNED TO | EFFORT | CUMULATIVE MAN-DAY EFFORT | STATUS | COMMENTS | PROGRESS | END/EXPECTED COMPLETION DATE | START | END |  | DAYS | time axis 2022-02-14 to 2022-04-17
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule. | bar: 2022-03-25; 2022-04-06
| 1 | OpenShift install | 1,2,3,C | John / Hung | 5 |  | Completed | Provisioned the envir | 100% | 2022-02-27 | 2022-02-21 | 2022-02-28
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | 2 | CP4D Install | 4 | John | 7 | 8 | Completed | John has installed to the internal system , Db will be installed next then Anindyo will be sharing with Son/Nars | 100% | 2022-02-27 | 2022-02-21 | 2022-02-27 |  | 7
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 2.1 | a) Verify environment | 4 | John |  |  | Completed |  | 100% | 2022-02-27 | 2022-02-21 | 2022-02-27 |  | 7
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | 2.2 | b) Copy binaries to Private Registry | 4 | John |  |  | Completed |  | 100% | 2022-02-27 | 2022-02-21 | 2022-02-27 |  | 7
| 2.3 | c) Foundation steps | 4 | John |  |  | Completed |  | 100% | 2022-02-27 | 2022-02-21 | 2022-02-27 |  | 7
| 2.4 | d) Install required services | 4 | John |  |  | Completed |  | 100% | 2022-02-27 | 2022-02-21 | 2022-02-27 |  | 7
| 3 | Manta Install | 1,2 | Anindyo | 2 | 7 | Completed | Manta has been set up | 100% | 2022-02-27 | 2022-02-21 | 2022-02-22
| 4 | Manta integration | 3 | Anindyo | 2 | 9 | On-Track | In progress | 0% | 2022-02-27 | 2022-02-23 | 2022-02-24
| 5 | Setup and Configuration (MANTA) | 2.4 , 4 | Anindyo | 3 | 10 | On-Track | In progress | 0% | 2022-02-27 | 2022-02-25 | 2022-02-27
| 6 | Testing in IBM E2E Integration Environment | 2 | Son / Nas | 10 |  | On-Track | In progress | 0% | 2022-03-09 | 2022-02-28 | 2022-03-09
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | 11 | Data Source Integration |  |  |  | 15 |  |  |  |  | 2022-02-21 | 2022-03-06 |  | 14
| 11.1 | Teradata integration (Substitute by DB2) | 5.3 | Son | 3 | 13 | Not Started |  | 0% | 2022-03-06 | 2022-02-28 | 2022-03-02 |  | 3
| 11.2 | Oracle integration | 5.3 | Son | 3 | 15 | On-Track | Pending Anindyo to look through - but completed. Should be completed tomorrow. | 80% | 2022-03-06 | 2022-02-21 | 2022-03-06 |  | 14
| 11.3 | SQL Server intgeration | 5.3 | Son | 3 | 15 | On-Track | Completed installation and integration, and now scanning in progress. Should be completed tomorrow. | 80% | 2022-03-06 | 2022-02-21 | 2022-03-06
| 11.4 | Qlik integration | 5.3 | Manta / Yongjia | 1 | 15 | On-Track | Shane has helped YJ with the file filter but SML Passing / Node script | 50% | 2022-03-06 | 2022-02-21 | 2022-03-06
| 11.5 | DCT file conversion | 5.3 | Yongjia | 1 | 15 | On-Track | The task as started as of 14th Feb 2022, and Pending reply from OCBC if the current format is aligned and E2E integration to be completed. | 80% | 2022-03-06 | 2022-02-21 | 2022-03-06
| 11.6 | Data Collection Template Integration | 5.3 | Nas | 3 | 15 | On-Track | Nas Set up and tested. Pending Anindyo to look through - but completed. Should be completed tomorrow. | 80% | 2022-03-06 | 2022-02-21 | 2022-03-06
| 11.7 | Hive integration | 5.3 | Paul | 2 | 15 | On-Track | installation completed and no major issues has arised > now move to integration - connect to JDBC + mimic to their envionrment > connect to WKC from JDBC and run discovery to test | 50% | 2022-03-06 | 2022-02-21 | 2022-03-06
| 11.8 | HDFS Integration | 5.3 | Paul | 2 | 15 | On-Track | installation completed and no major issues has arised > now move to integration | 50% | 2022-03-06 | 2022-02-21 | 2022-03-06
| 11.9 | Atlas (Cloudera) integration | 5.3 | Paul | 3 | 15 | On-Track | installation completed and no major issues has arised > now move to integration // Highlight as a potential risk | 50% | 2022-03-06 | 2022-02-21 | 2022-03-06
| 11.1 | Data files | 5.3 | Paul | 3 | 15 | On-Track | installation completed and no major issues has arised > now move to integration | 50% | 2022-03-06 | 2022-02-21 | 2022-03-06
| 11.11 | IGC integration + set up | 5.3 | Paul | 3 | 15 | On-Track | installation completed and no major issues has arised > now move to integration | 50% | 2022-03-06 | 2022-02-21 | 2022-03-06
```` | 11.12 | Kafka integration | 5.3 | Anindyo / Manta | 5 | 15 | Not Started | Kafka has been installed in the VM, API approach / Manta connection to source | 0% | 2022-03-06 | 2022-02-21 | 2022-03-06 |  | 14
| 11.13 | *Kafka Set-up | 5.3 | Anindyo | 1 | 15 | Not Started | CE has provided to Anindyo the Kafka set up // pending the machine from Anindyo | 0% | 2022-03-06 | 2022-02-21 | 2022-03-06 | 2022-02-21 | 2022-03-06
| 11.15 | *PowerBI Integration | 5.3 | Manta | 1 | 15 | On-Track | MANTA will import the PBI files > PBIT files was sent by OCBC Sri | 0% | 2022-03-06 | 2022-02-21 | 2022-03-06
| 12 | Technical Metadata capture using API
| 15.1 | a) Tables, Columns, Databases, Views, Schemas | 10-12.2 | Anindyo | 3 | #REF! | Not Started |  | 0% | 2022-03-09 | #REF! | #REF!
| 15.2 | b) Stored Procedures, Embedded SQLs, | 10-12.2 | Manta - Shane | 1 | #REF! | Not Started |  | 0% | 2022-03-09 | #REF! | #REF!
| 12.1 | Dynamic SQLs |  | Wei Lian / Arief / Manta - Shane | 10 | 10 | On-Track |  | 50% | 2022-03-09 | 2022-02-18 | 2022-02-27
| 15.4 | d) Custom | 10-12.2 | Anindyo | 5 | #REF! | Not Started |  | 0% | 2022-03-09 | #REF! | #REF!
| 13 | Generate Data Lineage |  |  |  | 17 |  |  |  |  | 0 | 2022-03-10
| 13.1 | General - Qlik, ETL, Stored Procedures, BTQmain, Teradata, SQL Server etc. | 12,14 | Manta / Yongjia / Son | 5 | 18 | On-Track | Qilk - YJ, BTQMain - Klook (YJ), Stored Procedures (IBM) | 50% | 2022-03-09 | 2022-02-21 | 2022-03-09
| 13.2 | Klook |  | Yongjia | 5 | 18 | On-Track | Note: Require validation from OCBC before testing, hence, the dates are not including the alignment session | 50% | 2022-03-09 | 2022-02-18 | 2022-03-09
| 17.3 | Dynamic SQL |  | Manta - Shane / Wei Lian / Arief | 15 | 16 | On-Track | Setting up meeting with Bhusan - to understand how we can send the output to MANTA // looking into microsoft SQL | 50% | 2022-03-09 | 2022-02-18 | 2022-03-09
| 17.4 | Run through the final integration between mantas and WKC |  | Susanna - WKC owner / Clement |  |  | On-Track | Clement has given Susanna a heads up and will set up with her | 50% | 2022-03-09 | 2022-02-18 | 2022-03-09
| 17.5 | IGC to WKC Sync up |  | Anindyo |  |  | Not Started |  |  | 2022-03-09 | 0 | 2022-03-10
|  | Evaluation Functionality Coverage (Validate) |  | All | 5 | 18 | Not Started | Dry-run & Collaborating with Jacob + feedback | 0% | 2022-03-09 | 2022-03-03 | 2022-03-09
| 19 | Walkthrough | 17 | [7 empty] | 2022-03-11 | 2022-03-11 |  | 1
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule.
my webex
slide - presented in RFP presentation > produce the skeleton
topics to discuss > time required for each section > 3.5 hours target to complete
1-2 buffer in between (3:45pm mark)
profiling need to br prioritise > so need to validate with the team
DO WE NEED ROS HERE? WL NEED TO GET HIS FEEDBACK > DYNAMIC SQL - MEETING ON THURSDAY WITH WL/ARIEF
Note on L3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As of 26 jan, OCBC still preparing the environment. Tentative: 3rd Feb Reply: As of 4th Feb, the tentative start date is 8th Feb Reply: As of 9th Feb, OCBC environment is ready for us but we need the dropbox access. This will determine the tentative start date.
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: the cumulative (total) man-day required to complete this task from the start of the project
Note on L6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to confirm the Effort day, and the Start + End date for the first stream of work
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: (double check with Son)
Note on L39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Critical Path: Task 5 (CP4D Install) Task 8 > Task 12 and Task 14

## Risk & Assumption log (hidden)
S/N | Task | Assumptions/Risk | Date | Owner (if applicable) | Any corrective action? (if applicable) | Overall Status | Other comments
1 | 1 | Assumption: 3 laptop provided by OCBC - Using Webex | 2022-01-21
2 | 1.1 | Clarification: Have we provided the OCP Pre-req to OCBC? | 2022-01-13 | Hung/John | Next steps: Yes, Infra + Domain name + Network is required. IBM will provide the pre-req to OCBC and review the list with OCBC. |  | Done - Resource available to help if required
3 | 14 | Risk: OCBC only provided the stored procedure, and not the sample data required. Without the sample data, it will pose as a risk. Scope of work: Oracle first | 2022-01-13 | Anindyo/WL/Arief | Next steps: Anindyo to clarify with OCBC – Anindyo will help provide the Oracle database to WL, – Anindyo will drop a message to Jacob to provide the sample data-set. Dependency is on the 17th Jan/Monday - start date. | Done | Pending - Anindyo will get the Oracle DB Instance pre-req for WL/Arief (As of 10th Feb) Done - as of 14th feb
4 | 15.2-3 | Clarification: Technical Metadata capture using API b) Stored Procedures, Embedded SQLs, c) Dynamic SQLs - scope of work and details? | 2022-01-13 | Anindyo/Shane/WL/Arief | Next steps: speak to Shane on 18th Jan evening to finalised the details | Done | Pending - Anindyo and Clement will get into a call and get back from Shane (as of 10th feb)
5 | 11.1 | Risk: Cloudera integration require exploration from Paul because he has no prior experience | 2022-01-17 | Anindyo/Paul | Next steps: - Anindyo to help prepare the CP4D access and 2 VM (Single node) for both IGC and Atlas (Cloudera) integration + Share any documentation with Paul | Done | Pending - CE will provide support if required. Vavarly will reach out to Paul to understand the progress/status. Done - as of 14th feb
6 | 11.4 | Assessment required - Qilk: Qilkview is what OCBC POC criteria has requested for BUT IBM/Manta could only support Qilksense (latest version) | 2022-02-16 |  | Risk: Require further assessment on this technical constraint. OCBC x IBM Checkpoint call (17 feb): We can double check with Jacob - if there is any upgrades on Qilk and to verify. Internal next steps: > Further clarify with Shane whether they can support (Daryl) - done > Communicate with Management that we have a gap in the POC. (Clement > Denise) | On-track | As of 21st Feb, We will demonstrate on our environment with MANTA help
8 | 2 | Risk: Trial license might become a dependency Because it will require OCBC to reply back to IBM to fulfil the requirement | 2022-01-26 | Clement |  | Done | Done: OCBC has acknowledge and accepted the trial license clause
9 |  | Risk: Timeline delayed to tentative start date to 14th Feb | 2022-02-03 | Clement / Anindyo |  | Done | Done: OCBC Environment is ready, but Dropbox access for file transfering still pending
10 |  | Risk: OCBC will only provide VM and IBM will install OCP | 2022-02-04 | Clement |  | Done | Accepted the risk, and the team will work with this assumption
11 |  | Risk: Shane has not shared any time slot to guide us through the Klook integration with Anindyo | 2022-02-07 | Clement |  | Done | Done - after speaking to MANTA, YJ from CE will take over the task
12 |  | Risk: Simulation of the POC Environment is not done and ready | 2022-02-11 | Anindyo / IBM Team |  | On-track | both of Son and Nars are helping with the E2E integration flow simulated in iBM Testing environment
13 |  | Assessment required - PowerBI: Not compatible with OCBC version | 2022-02-14 |  | Internal next steps: > Further clarify with Shane whether they can support (Daryl) - done | On-track | As of 21st Feb, We will demonstrate on our environment with MANTA help
14 |  | Harddisk file transfer is an issue and delayed longer than expected IBM Team faced issues conducting file transfer successfully in OCBC sit as it is slow/failing - YMAL (RHOCP) installation has issues and Lumeng from OCBC has helped addressed it | 2022-02-16 |  | As of 21st Feb, All file transfer have been completed at the OCBC Landing server which is under OCBC - Muttu but we need to complete the transfer to the final server that IBM team require to start the installation. However, Muttu have not replied on the progress to OCBC Vivek and IBM Team since he is sick. This issue has been highlighted as a dependency for the project since 16th Feb. | Risk | Dependency to start any installation in the OCBC environment for our POC progression
15 |  | Dynamic SQL IBM (WL) need to proceed down to OCBC site to view the environment and determine the necessary execution and implementation next steps. - To gain confidence level in the accuracy of the output file being call out, we need to understand the how the pattern of the syntax being captured and be part of the implementation design | 2022-02-17 |  | Next steps: OCBC will schedule a call on 18th feb to share the necessary inputs and the environment with WL so that he gather as much input to conduct his own task | On-track
16 |  | Deadline cannot be extended further than 9th March. OCBC has shared that the deadline cannot be further than 9th March 2022, and it need to be completed by then. |  |  | Next steps: 1. IBM need to work out a project schedule that will meet the deadline of 9th March (completion date) and 10th March (presentation date). As a team, we need to decide if can work over the weekend especially since OCBC offered this suggestion. 2. Inform MANTA about the deadline, and require his time during the daily stand up which we will shift from 830am to 9pm in the evening from 28th feb onwards 3. Especially during the week of 28th feb - 6th March where we need to complete the data source integration. Suggest to do as much testing as possible, and so that you can execute on 28th feb and focus on troubleshooting. | Pending
17 |  | Risk: Shane from MANTA is leaving the firm on 28th Feb, hence, Shane has introduced the new engineer (Busan) which the IBM internal team need to start collaborating asap |  |  | IBM has daily interlock with Shane - MANTA with the new engineer to ensure we are all in sync on the next steps | On-track

## Duty Rooster (On-site) (hidden)
Context: We need 2 pax to be on the ground in OCBC to be working on-site (As of 14/2 as start date)
|  | Wei Lian | Arief | John Isaac | Son | Anindyo | Hung | Paul | Clement | YJ | Ronny | Comments
| Week 1 - (17/1-21/1) | 0 | 0 | 5 | 2 | 1 | 5 | 0 | 0 |  | 0
| 2022-01-17 |  |  | 1 |  |  | 1
| 2022-01-18 |  |  | 1 | 1 | 1 | 1
| 2022-01-19 |  |  | 1 | 1 |  | 1
| 2022-01-20 |  |  | 1 |  |  | 1
| 2022-01-21 |  |  | 1 |  |  | 1
| Week 2 - (24/1 - 28/1) | 0 | 0 | 5 | 0 | 3 | 4 | 0 | 0 |  | 0
| 2022-01-24 |  |  | 1 |  | 1 | 1
| 2022-01-25 |  |  | 1 |  | 1 | 1
| 2022-01-26 |  |  | 1 |  | 1 | 1
| 2022-01-27 |  |  | 1 |  |  | 1
| 2022-01-28 |  |  | 1
| Week 1 - (31/1 - 4/2) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0
2022-01-31
2022-02-01
2022-02-02
2022-02-03
` | 2022-02-04
``` | Week 2 - (7/2 - 11/2) | 0 | 0 | 4 | 0 | 3 | 4 | 0 | 3 |  | 0
2022-02-07
| 2022-02-08 |  |  | 1 |  | 1 | 1 |  | 1
| 2022-02-09 |  |  | 1 |  | 1 | 1 |  | 1
| 2022-02-10 |  |  | 1 |  | 1 | 1 |  | 1
``` | 2022-02-11 |  |  | 1 |  |  | 1
| Week 1 - (14/2 - 18/2) | 1 | 1 | 5 | 0 | 5 | 0 | 0 | 3 | 0 | 0
| 2022-02-14 |  |  | 1 |  | 1 |  |  | 1 |  |  | Start date
| 2022-02-15 |  |  | 1 |  | 1 |  |  | 1
| 2022-02-16 |  |  | 1 |  | 1 |  |  | 1
| 2022-02-17 | 1 | 1 | 1 |  | 1
| 2022-02-18 |  |  | 1 |  | 1
| Week 2 - (21/2 -25/2) | 0 | 0 | 5 | 3 | 5 | 5 | 0 | 0 | 0 | 0
| 2022-02-21 |  |  | 1 |  | 1 | 1
| 2022-02-22 |  |  | 1 |  | 1 | 1
| 2022-02-23 |  |  | 1 | 1 | 1 | 1
| 2022-02-24 |  |  | 1 | 1 | 1 | 1
| 2022-02-25 |  |  | 1 | 1 | 1 | 1
| Week 3 - (28/2 -4/3) | 0 | 0 | 5 | 2 | 5 | 5 | 0 | 0 | 0 | 0
| 2022-02-28 |  |  | 1 | 1 | 1 | 1
| 2022-03-01 |  |  | 1 | 1 | 1 | 1
| 2022-03-02 |  |  | 1 |  | 1 | 1
| 2022-03-03 |  |  | 1 |  | 1 | 1
| 2022-03-04 |  |  | 1 |  | 1 | 1
| Week 4 - (7/3 -11/3) | 0 | 0 | 0 | 5 | 5 | 0 | 5 | 0 | 5 | 0
| 2022-03-07 |  |  |  | 1 | 1 |  | 1 |  | 1
| 2022-03-08 |  |  |  | 1 | 1 |  | 1 |  | 1
| 2022-03-09 |  |  |  | 1 | 1 |  | 1 |  | 1
| 2022-03-10 |  |  |  | 1 | 1 |  | 1 |  | 1
| 2022-03-11 |  |  |  | 1 | 1 |  | 1 |  | 1
| Week 5 - (14/3 -18/3) | 5 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 2
| 2022-03-14 | 1 | 1 |  |  | 1 |  |  |  |  | 1
| 2022-03-15 | 1 | 1 |  |  | 1 |  |  |  |  | 1
| 2022-03-16 | 1 | 1 |  |  | 1
| 2022-03-17 | 1 | 1 |  |  | 1
| 2022-03-18 | 1 | 1 |  |  | 1
| Week 6 - (21/3 -25/3) | 5 | 5 | 0 | 0 | 5 | 0 | 0 | 0 | 3 | 0
| 2022-03-21 | 1 | 1 |  |  | 1 |  |  |  | 1
| 2022-03-22 | 1 | 1 |  |  | 1 |  |  |  | 1
| 2022-03-23 | 1 | 1 |  |  | 1 |  |  |  | 1
| 2022-03-24 | 1 | 1 |  |  | 1
| 2022-03-25 | 1 | 1 |  |  | 1
| Week 7 - (28/3 -1/4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2022-03-28
2022-03-29
2022-03-30
2022-03-31
2022-04-01
| Week 8 - (4/4 -8/4) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2022-04-04 | [10 empty] | End-date
2022-04-05
2022-04-06
2022-04-07
2022-04-08
Shane- Mantas, Overall POC owner for MANTAS based in Ireland, hence, there is no need to hold the physical space.

## Team Structure (hidden)
Team Member
Wei Lian - Dynamic SQL
Areif - Dynamic SQL
Shane - Mantas, Overall POC owner
John Isaac - OpenShift & CP4D Instalation
Son - CP4D install, WKC Functional out of the box
Anindyo - WKC Functional APIs and Manta install
Ronny - Data Quality
Hung - OpenShift install
Juanda Zeng - RH Openshift (+65 9247 4347 & jzeng@redhat.com)
Abhishek - RH Assistance (Abhishek.Vijra@ibm.com)
Vavarly - PM
Ros Davis - SME support
Paul

## Project Schedule (Old draft) (hidden)
Create a Project Schedule in this worksheet. Enter title of this project in cell B1. Information about how to use this worksheet, including instructions for screen readers and the author of this workbook is in the About worksheet. Continue navigating down column A to hear further instructions. |  | OCBC Data Lineage RFP - POC | [9 empty] | 2022-02-14
Enter Company Name in cell B2.
Enter the name of the Project Lead in cell B3. Enter the Project Start date in cell E3. Pooject Start: label is in cell C3. |  | Scope: OCBC Data Lineage RFP includes - Data Profiling | [8 empty] | Project Start: | 2022-02-14
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. | [10 empty] | Display Week: | 1 |  |  |  | 2022-02-14 | [6 empty] | 2022-02-21 | [6 empty] | 2022-02-28 | [6 empty] | 2022-03-07 | [6 empty] | 2022-03-14 | [6 empty] | 2022-03-21 | [6 empty] | 2022-03-28 | [6 empty] | 2022-04-04 | [6 empty] | 2022-04-11
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-02-14 to 2022-04-17
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | S/N | TASK | DEPENDENCIES | ASSIGNED TO | Tested in IBM Environment? | EFFORT | CUMULATIVE MAN-DAY EFFORT | STATUS | COMMENTS | PROGRESS | END/EXPECTED COMPLETION DATE | START | END |  | DAYS | time axis 2022-02-14 to 2022-04-17
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule. | bar: 2022-03-25; 2022-04-06
| A | Testing in IBM Environment |  | Hung / John / Son |  |  |  | Completed |  | 100% |  | 2022-01-18 | 2022-01-18
| B | Dropbox access (file 8.6 gb) |  | OCBC / Clement / Anindyo |  | 2 |  | On-Track | Small files in Dropbox, but oCBC has not been notified > have not enabled the hard disk // Anindyo will go on site today | 100% |  | 2022-02-14 | 2022-02-15
| C | Harddisk access |  | OCBC / Anindyo / John |  | 5 | 1 | On-Track | OCBC has provided 2 machine > IBM has 2 hard disk ready for file transfer (done concurrently) and best-case: complete the file transfer by 18th Feb EOD Been bale to move one part, but there are some file missing > the other two copy is initiated > part 3: 30% done + MANTA file is transferred + YMAL issue has been resolved > speak to vivek to resolve the challenge | 50% | 2022-02-18 | 2022-02-14 | 2022-02-18 | 2022-02-14 | 2022-02-14
| 1 | Env readiness (VMs) |  | OCBC (Parteek/Clement) |  |  |  | Completed | Update: OCBC will provide the VM and IBM will do the OCP installation | 100% |  | 2022-02-14 | 2022-02-14
| 1.1 | OCP Pre-requsitie (Domain name and Network) |  | Hung / John |  | 1 | 1 | Completed |  | 100% |  | 2022-02-14 | 2022-02-14
| 1.2 | OCP installation (Redhat) |  | Hung / John |  | 1 | 1 | Completed |  | 100% |  | 2022-02-14 | 2022-02-14
| 1.3 | Share the hard disk to Anindyo |  | Daryl |  |  |  | Completed |  | 100% |  | 2022-01-13 | 2022-01-13
| 1.4 | Provide the link url and get the RH assistance resource to our upcoming meeting cadence |  | John |  |  |  | Completed |  | 100% |  | 2022-01-13 | 2022-01-13
| 2 | Trial License |  | Clement |  | 3 | 3 | Completed | Clement has send a follow up to respond on whether the specific clause (provided by OCBC) is sufficient. // OCBC has replied on the approval of the license agreement | 100% |  | 2022-02-14 | 2022-02-16
| 3 | Download binaries to local repo |  | Son / Hung |  | 3 |  | Completed |  | 100% |  | 2022-01-14 | 2022-01-18
| 4 | OpenShift install | 1,2,3,C | John / Hung |  | 5 |  | Not Started | Hung might not be able to get down onsite, Anindyo / OCBC might be setting up | 0% | 2022-02-27 | 2022-02-21 | 2022-02-25
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | 5 | CP4D Install | 4 | John |  | 7 | 8 | Not Started | Hung Downloaded CP4D v 4.0.5 but has some issue, John will conduct the download and check the progress | 0% | 2022-02-27 | 2022-02-21 | 2022-02-27 |  | 7
Cell B9 contains the sample task "Task 1." Enter a new task name in cell B9. Enter a person to assign the task to in cell C9. Enter progres of the task in cell D9. A progress bar appears in the cell and is shaded according to the number in the cell. For example, 50 percent progress would shade half of the cell. Enter task start date in cell E9. Enter task end date in cell F9. A status bar shaded for the dates entered appears in blocks starting from cell I9 through BL9. | 5.1 | a) Verify environment | 4 | John |  |  |  | Not Started |  | 0% | 2022-02-27 | 2022-02-21 | 2022-02-27 |  | 7
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | 5.2 | b) Copy binaries to Private Registry | 4 | John |  |  |  | Not Started |  | 0% | 2022-02-27 | 2022-02-21 | 2022-02-27 |  | 7
| 5.3 | c) Foundation steps | 4 | John |  |  |  | Not Started |  | 0% | 2022-02-27 | 2022-02-21 | 2022-02-27 |  | 7
| 5.4 | d) Install required services | 4 | John |  |  |  | Not Started |  | 0% | 2022-02-27 | 2022-02-21 | 2022-02-27 |  | 7
| 6 | Manta Install | 1,2,3 | Anindyo |  | 2 | 7 | Not Started | Klook Integration | 0% | 2022-02-27 | 2022-02-21 | 2022-02-22
| 7 | Manta integration | 6 | Anindyo |  | 2 | 9 | Not Started |  | 0% | 2022-02-27 | 2022-02-23 | 2022-02-24
| 8 | Setup and Configuration (MANTA) | 5.4 , 6 | Anindyo |  | 3 | 13 | Not Started |  | 0% | 2022-02-27 | 2022-02-28 | 2022-03-02
| 9 | LDAP Integration | 5.3 | Anindyo |  | 2 | 15 | Not Started | Next steps: Double confirm + Ensure iBM have the URL for the AD esp since we are in UAT Environment | 0% | 2022-02-27 | 2022-03-02 | 2022-03-04
| 10 | Setup Data Quality Rules | 8 | Ronny |  | 2 | 17 | Not Started |  | 0% | 2022-02-27 | 2022-03-07 | 2022-03-08
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | 11 | Data Source Integration |  |  |  |  | 15 |  |  |  |  | 2022-02-28 | 2022-03-04 |  | 5
| 11.1 | Teradata integration | 5.3 | Son |  | 3 | 13 | Not Started |  | 0% | 2022-03-06 | 2022-02-28 | 2022-03-02 |  | 3
| 11.2 | Oracle integration | 5.3 | Son |  | 3 | 13 | Not Started |  | 0% | 2022-03-06 | 2022-02-28 | 2022-03-02 |  | 3
| 11.3 | SQL Server intgeration | 5.3 | Son |  | 3 | 13 | Not Started |  | 0% | 2022-03-06 | 2022-02-28 | 2022-03-02
| 11.12 | IGC integration + set up | 5.3 | Paul |  | 3 | 13 | Not Started | Note: OCBC will not providing IGC in POC environment | 0% | 2022-03-06 | 2022-02-28 | 2022-03-02
```` | 11.13 | Kafka integration | 5.3 | Anindyo |  | 5 | 15 | Not Started |  | 0% | 2022-03-06 | 2022-02-28 | 2022-03-04 |  | 5
| 11.14 | *Kafka Set-up | 5.3 | Anindyo |  | 1 | 11 | Not Started | CE has provided to Anindyo the Kafka set up // pending the machine from Anindyo | 0% | 2022-03-06 | 2022-02-28 | 2022-02-28
Sample phase title block | 12 | Business Metadata capture using GUI |  | Son |  |  | 16 |  |  |  |  | 2022-03-03 | 2022-03-07 |  | 5
| 12.1 | a) Classifications, Categories, Data Classes, Business Terms | 8 | Son |  | 3 | 16 | Not Started |  | 0% | 2022-03-09 | 2022-03-03 | 2022-03-07 |  | 5
| 12.2 | b) Custom | 8 | Son |  | 3 | 16 | Not Started |  | 0% | 2022-03-09 | 2022-03-03 | 2022-03-07 |  | 5
| 13 | Business Metadata capture using API |  | Anindyo |  |  | 16 |  |  |  |  | 2022-03-02 | 2022-03-07 |  | 6
| 13.1 | a) Classifications, Categories, Data Classes, Business Terms | 5.3 | Anindyo |  | 3 | 15 | Not Started |  | 0% | 2022-03-09 | 2022-03-02 | 2022-03-04 |  | 3
| 13.2 | b) Custom | 8 | Anindyo |  | 3 | 16 | Not Started |  | 0% | 2022-03-09 | 2022-03-03 | 2022-03-07 |  | 5
Sample phase title block | 14 | Technical Metadata capture using GUI |  |  |  |  | 20 |  |  |  |  | 2022-03-09 | 2022-03-11 |  | 3
| 14.1 | Pre-req: Communicate with Jacob to provide the sample data-set & provide the ORACLE DB INSTANCE | 1 | Anindyo |  |  |  | Completed | Request: Anindyo will help provide the Oracle database instance to WL and Arief (10/2) - Anindyo has requested for help from support but pending | 100% | 2022-03-09 | 2022-02-14 | 2022-02-14
| 14.2 | a) Tables, Columns, Databases, Views, Schemas | 10-12.2 | Son |  | 3 | 20 | Not Started |  | 0% | 2022-03-09 | 2022-03-09 | 2022-03-11 |  | 3
| 14.3 | b) Stored Procedures, Embedded SQLs, | 10-12.2 | Manta - Shane |  | 1 | 18 | Not Started |  | 0% | 2022-03-09 | 2022-03-09 | 2022-03-09 |  | 1
| 14.4 | d) Custom | 10-12.2 | Wei Lian / Arief |  | 3 | 20 | Not Started |  | 0% | 2022-03-09 | 2022-03-09 | 2022-03-11 |  | 3
| 15 | Technical Metadata capture using API |  |  |  |  | 27 |  |  |  |  | 2022-03-09 | 2022-03-22
| 15.1 | a) Tables, Columns, Databases, Views, Schemas | 10-12.2 | Anindyo |  | 3 | 20 | Not Started |  | 0% | 2022-03-09 | 2022-03-09 | 2022-03-11
| 15.2 | b) Stored Procedures, Embedded SQLs, | 10-12.2 | Manta - Shane |  | 1 | 18 | Not Started |  | 0% | 2022-03-09 | 2022-03-09 | 2022-03-09
| 15.3 | c) Dynamic SQLs | 10-12.2 | Wei Lian / Arief / Manta - Shane |  | 10 | 27 | Not Started |  | 0% | 2022-03-09 | 2022-03-09 | 2022-03-22
| 15.4 | d) Custom | 10-12.2 | Anindyo |  | 5 | 22 | Not Started |  | 0% | 2022-03-09 | 2022-03-09 | 2022-03-15
| 17 | Walkthrough | [9 empty] | 2022-03-23 | 2022-03-25
| 17.5 | Evaluation Functionality Coverage (Validate) |  | All |  | 1 | 30 | Not Started | Dry-run & Collaborating with Jacob + feedback | 0% | 2022-03-09 | 2022-03-23 | 2022-03-25
| 19 | Walkthrough | 17 | [8 empty] | 2022-03-28 | 2022-03-28 |  | 1
This is an empty row
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule.
DO WE NEED ROS HERE? WL NEED TO GET HIS FEEDBACK > DYNAMIC SQL - MEETING ON THURSDAY WITH WL/ARIEF
Note on M3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: As of 26 jan, OCBC still preparing the environment. Tentative: 3rd Feb Reply: As of 4th Feb, the tentative start date is 8th Feb Reply: As of 9th Feb, OCBC environment is ready for us but we need the dropbox access. This will determine the tentative start date.
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: the cumulative (total) man-day required to complete this task from the start of the project
Note on M6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to confirm the Effort day, and the Start + End date for the first stream of work